Renewable Energy Projects in the Philippines

Permits, Social Engagement & Grievance Redress — Quick Reference

Key issuances: RA 9513 · DC2024-06-0018 · DO2024-04-0003 · PD 1586 · RA 8371 · RA 7160 · DAO 2025-20 · DAO 2026-09

WHAT'S NEW — APRIL 2026 UPDATE

✦  EVOSS resumed 25 November 2024 after 5-month enhancement pause (Jun–Nov 2024). COA now fully integrated into EVOSS application flow.

✦  NEW: CEPNS DO 2024-04-0003 (April 2024) revised framework; 149 projects (17.6 GW RE) certified May–Dec 2024. Enables simultaneous permit processing and presumption of issuance.

✦  DENR-EMB — FPV: DAO 2025-20 issued: specific ECC guidelines for Floating PV on inland freshwater bodies (Category B). Amended by DAO 2025-30. Applies retroactively to previously issued ECCs.

✦  DENR-EMB — Offshore Wind: DAO 2026-09 issued: enhanced ECC guidelines specifically for OSW projects. Previously issued OSW ECCs subject to review.

✦  DENR-PAMB / Protected Areas: DENR MO 2025-01 updated EIA process for projects in PAs, Ramsar sites, and Verde Island Passage Marine Corridor (VIPMC).

✦  GEAP updates: GEA-3 Notice of Award issued (hydro/geothermal). GEA-4 underway targeting 9,000+ MW (solar, wind, integrated solar+BESS).

✦  DOE enforcement active: Verify latest contract revocation figures with DOE-REMB — enforcement of social acceptability and SE documentation requirements is ongoing.

How to Use This Guide

→  Agency Permit Matrix — lists every key permit, attached SE and GRM obligations, governing issuance, and rough timeline.

→  Project Roadmap — shows which permits and activities occur at each project stage for correct sequencing.

→  Sequencing rule: Barangay Clearance first. FPIC/CP and ECC are the longest-lead permits — start both early and run concurrently.

→  CEPNS holders may process permits simultaneously across agencies — but social acceptability documentation remains mandatory regardless of CEPNS status.

→  FPV and OSW projects now have technology-specific ECC guidelines — use DAO 2025-20 / DAO 2026-09 in addition to the standard PD 1586 / DAO 2003-30 pathway.

Agency Permit Matrix

| Agency | Key Permit / Approval | SE Requirement | GRM Requirement | Key Issuance / Document | Timeline | Stage |
| --- | --- | --- | --- | --- | --- | --- |
| DOE | Certificate of Authority (COA) Enables pre-feasibility & permit processing before 25-yr contract. Submitted via EVOSS (fully resumed Nov 25, 2024). | Initial LGU briefing Community consultations Letter of Intent via EVOSS | Issue resolution log Document early concerns raised | DC2024-06-0018 Revised Omnibus RE Guidelines (June 2024 — replaces DC2019-10-0013) EVOSS resumed: 25 Nov 2024 | 1–3 months | Pre-Dev |
| DOE NEW | Certificate of Energy Projects of National Significance (CEPNS) Enables simultaneous permit processing across all agencies. Auto-qualifies: FIT-eligible, GEAP winners, projects ≥ PHP 3.5B. Valid until Commercial Operations Date. | Social acceptability still required with CEPNS All standard LGU, NCIP, and ECC consultations remain | CEPNS does not waive GRM obligations Community engagement requirements unchanged | DO 2024-04-0003 Revised CEPNS Framework (April 2024) Administered by DOE Investment Promotion Office via EICC / EO 30 | Varies | Pre-Dev Dev |
| DOE | RE Service / Operating Contract 25-year contract; awarded via EVOSS. GEAP-3 Notice of Award issued (hydro/geothermal). GEAP-4 ongoing (9,000+ MW solar, wind, solar+BESS). | LGU endorsements (barangay + municipal) Documented consultations with attendance sheets Proof of social acceptability Minutes of community meetings | Grievance log submitted pre-award All community issues resolved or with action plan DOE as escalation forum (contractual basis) | DC2024-06-0018 CBREDa Guidebook (DOE-REMB best practice for social preparation) | 3–6 months | Dev Stage |
| DENR–EMB UPDATED | ECC or Certificate of Non-Coverage (CNC) Standard: PD 1586 / DAO 2003-30. FPV (inland water): DAO 2025-20/2025-30 — applies to all FPV including previously issued ECCs. Offshore Wind: DAO 2026-09 — OSW ECCs subject to DENR review. | Public scoping (EMB-facilitated) EIA consultations at each stage Disclosure of impacts & mitigation IEC campaigns FPV: Project Description for Scoping Report (PDS) required | Project-level GRM established Multi-partite Monitoring Team (MMT) formed Grievance log maintained Non-compliance = ECC violation SMRs & CMRs submitted to EMB RO | PD 1586 + DAO 2003-30 DAO 2017-15 (Public Participation) DAO 2025-20 (FPV-specific) DAO 2025-30 (FPV amendment) DAO 2026-09 (OSW-specific) | 3–12 months | Pre-Dev Dev |
| DENR–PAMB UPDATED | Protected Area Clearance For projects in NIPAS, Ramsar sites, or VIPMC. DAO 2026-09 also governs RE in PAs for OSW. DENR Secretary approval required. | PAMB multi-stakeholder review EMB Director clearance of Technical Scoping Checklist Social development plan integration | PAMB oversight mechanism Formal multi-stakeholder board review | DENR MO 2025-01 Updated EIA guidelines for PAs, Ramsar sites & VIPMC (amends MO 2023-01 and 2023-04) DAO 2026-09 Sec. 5 (RE in PAs) | 3–6 months | Pre-Dev |
| NCIP | Certification Precondition (CP) / FPIC Applies if project overlaps or affects ancestral domain. No CP = no permit or license can be granted. | Min. 2 community assemblies Field-Based Investigation (FBI) by NCIP ESIS (Enviro & Socio-Cultural Impact Statement) Full disclosure in local language | Tiered process: community → NCIP field → NCIP Central MOA must include grievance mechanism No CP = no permit or license can be granted | IPRA (RA 8371) NCIP AO No. 3 s.2012 (FPIC Guidelines) FBI fee: PHP 5,000; FPIC fee varies by scope | 3–6 months+ | Pre-Dev |
| LGU–Barangay | Barangay Clearance Must be secured FIRST, before any other LGU permit. | Barangay assembly Community consultation documentation Barangay resolution | Barangay grievance desk First-line GRM platform for community complaints | RA 7160 Sec. 26 & 27 Barangay resolution required | 1–2 weeks | Pre-Dev |
| LGU–Municipal / City | Mayor's Permit · Zoning / Locational Clearance · Building & Electrical Permit Requires Barangay Clearance first. Zoning must align with CDP/CLUP. | Sanggunian consultation (RA 7160 Sec. 27) CDP/CLUP alignment Public hearing for zoning issues DILG MC 2022: no LONO unless PEISS satisfied | Municipal complaint office Sanggunian hearing mechanism Mayor's office intervention | RA 7160 Sec. 26 & 27 DENR-DILG JMC 98-01 DILG MC 2022 (LONO conditions) | 2–4 weeks | Dev Pre-Con |
| ERC | PSA Approval · Certificate of Compliance (COC) / Provisional Authority to Operate (CPOA) Applies to grid-connected & distribution-tied RE projects. | Mandatory public hearings Consumer and stakeholder participation Rate and contract transparency | Formal complaint process ERC decisions appealable to courts Rate and service quality complaints | ERC Rules of Practice & Procedure ERC Customer Service & Complaints Rules | Variable | Dev Ops |
| NWRB | Water Permit Hydropower projects only. | Water permit consultations Objections hearing process | Quasi-judicial dispute resolution Protest process during permit processing | Water Code (PD 1067) Coordinate with FPIC / ECC if in or near ancestral domain or watershed | 3–6 months | Pre-Dev |
| DAR | Land Use Conversion Agricultural land only; required before RE development can proceed. | ARB (Agrarian Reform Beneficiary) consultation Land tenure disclosure Notice of Land Use Conversion | Tenure-related grievance process DAR mediation mechanism | CARP (RA 6657) DAR AO on land use conversion | 3–9 months | Pre-Dev |

⚠  VERIFICATION REQUIRED

Verify the EVOSS documentary checklist (DOE-REMB) and confirm specific social acceptability requirements for each RE technology type with legal counsel before finalizing compliance documentation. DAO 2025-20 and DAO 2026-09 include technology-specific ECC pathways that may not yet be reflected in existing project ECCs.

Project Roadmap · Permit & SE Sequencing

Read across each row to see when each permit and SE activity occurs.  ● = Active in this stage   ○ = Not in this stage

| Agency | Permit / Activity | Pre-Dev (COA) | Dev (ECC) | Pre-Con | Construction | Ops & Monitoring |
| --- | --- | --- | --- | --- | --- | --- |
| DOE |  |  |  |  |  |  |
| DOE | Letter of Intent → COA application (EVOSS) | ● | ○ | ○ | ○ | ○ |
| DOE ★NEW | CEPNS application (if qualifying) → simultaneous permit processing | ● | ● | ○ | ○ | ○ |
| DOE | LGU & community briefings (social acceptability proof) | ● | ● | ○ | ○ | ○ |
| DOE | RE Service / Operating Contract (EVOSS award) | ○ | ● | ○ | ○ | ○ |
| DOE | DOE contract monitoring & compliance reporting | ○ | ○ | ○ | ● | ● |
| DENR–EMB |  |  |  |  |  |  |
| DENR–EMB | ECC — Scoping & EIA preparation | ● | ● | ○ | ○ | ○ |
| DENR–EMB | ECC — Public consultations & ECC issuance | ○ | ● | ○ | ○ | ○ |
| DENR–EMB ↑UPD | FPV ECC pathway (DAO 2025-20 / DAO 2025-30) — if FPV on inland water | ● | ● | ○ | ○ | ○ |
| DENR–EMB ★NEW | OSW ECC pathway (DAO 2026-09) — if offshore wind | ● | ● | ○ | ○ | ○ |
| DENR–EMB | MMT formation & monitoring (post-ECC) | ○ | ○ | ● | ● | ● |
| DENR–PAMB |  |  |  |  |  |  |
| DENR–PAMB ↑UPD | Protected Area clearance (if applicable — now governed by DENR MO 2025-01) | ● | ○ | ○ | ○ | ○ |
| NCIP |  |  |  |  |  |  |
| NCIP | FPIC — Field-based investigation & community assemblies | ● | ○ | ○ | ○ | ○ |
| NCIP | FPIC — ESIS, MOA, Certification Precondition (CP) | ● | ● | ○ | ○ | ○ |
| NCIP | Post-consent monitoring & MOA compliance | ○ | ○ | ● | ● | ● |
| LGU |  |  |  |  |  |  |
| LGU–Barangay | Barangay Clearance (must be first) | ● | ○ | ○ | ○ | ○ |
| LGU–Barangay | Ongoing community liaison & grievance desk | ○ | ● | ● | ● | ● |
| LGU–Municipal | Zoning / Locational Clearance | ● | ○ | ○ | ○ | ○ |
| LGU–Municipal | Mayor's Permit & Building / Electrical Permit | ○ | ○ | ● | ○ | ○ |
| LGU–Municipal | Annual business permit renewal | ○ | ○ | ○ | ○ | ● |
| ERC / NWRB / DAR |  |  |  |  |  |  |
| ERC | Power Supply Agreement / COC / CPOA | ○ | ● | ● | ○ | ○ |
| ERC | Rate approval & consumer hearings | ○ | ○ | ○ | ○ | ● |
| NWRB | Water Permit (hydro projects only) | ● | ○ | ○ | ○ | ○ |
| DAR | Land Use Conversion (agricultural land only) | ● | ● | ○ | ○ | ○ |

KEY RULE OF THUMB FOR SE & GRM COMPLIANCE

If a grievance reaches a national agency or the courts, it is a sign that earlier LGU-level GRM failed. Weak SE or ineffective GRM is the most common legal vulnerability in RE projects — and can delay or revoke DOE contracts. Social acceptability must be demonstrated through documented processes, not just endorsement letters. CEPNS status does not waive community engagement or social acceptability requirements. FPV and OSW projects now have technology-specific ECC obligations — review DAO 2025-20 and DAO 2026-09 with your DENR-EMB Regional Office. DOE enforcement of contract compliance remains active; verify latest revocation data with DOE-REMB.