# Dependencies

## 1. Finish-to-Start (FS)

Definition: Task A must finish before Task B can start.

Example:

- Task A: Finalize learning objectives

- Task B: Begin storyboarding module content

You can’t start storyboarding until the objectives are finalized to guide the content.

## 2. Start-to-Start (SS)

Definition: Task B can start once Task A starts (they may run in parallel).

Example:

- Task A: Begin drafting module content

- Task B: Begin gathering multimedia assets

Once content drafting begins, you can also start sourcing videos or images based on that content.

## 3. Finish-to-Finish (FF)

Definition: Task B can only finish once Task A is finished.

Example:

- Task A: Complete quiz questions for all modules

- Task B: Finalize the course assessment package

You can’t finish compiling the full assessment package until all quizzes are completed.

## 4. Start-to-Finish (SF)

Definition: Task B cannot finish until Task A starts (least common).

Example:

- Task A: Start reviewing student support documentation

- Task B: Finalize faculty orientation guide

The orientation guide can’t be finalized until student support materials are reviewed to ensure consistency, so its completion depends on the other task starting.