FIVE-YEAR STRATEGIC PLAN

City of Clearhaven Ridge (Demonstration Only)
(For Demonstration Purposes Only)

DISCLAIMER: All figures, assumptions, projects, names, and performance measures in this document are fictional and provided solely for demonstrations, training, proposal samples, and marketing collateral. This document does not represent any actual municipality.

Table of Contents

Executive Overview (Executive Page)

Executive Summary

1. Planning Approach & Engagement Model

2. Vision, Mission & Values

3. Strategic Planning Principles

4. Strategic Goal Areas

5. Strategic Outcomes

6. Engagement-Focused Strategic Initiatives (A–G)

7. Implementation & Accountability

8. Financial & Budget Alignment

9. Ongoing Review & Engagement

10. Conclusion

Appendix A: Facilitated Retreat Agenda & Materials

Appendix B: Stakeholder Engagement Map & Communications Plan

Appendix C: Five-Year Operating Forecast (Detail)

Appendix D: Department Budgets & Staffing Plan

Appendix E: Five-Year CIP (Projects, Funding, Cash Flow)

Appendix F: Debt & Fund Balance Policy Exhibits

Appendix G: Performance Scorecards & Dashboard Mockups

Executive Overview (Executive Page)

City of Clearhaven Ridge (Demonstration Only) is a fictional, mid-sized community used to demonstrate an engagement-driven strategic planning deliverable.This plan demonstrates how a consultant can translate governing-body priorities and stakeholder input into:

• A five-year service and capital roadmap

• A budget and long-range forecast that supports policy trade-offs

• A performance management approach with clear accountability

Planning horizon: Five years. This plan uses mock financial data, a mock capital program, and mock performance baselines/targets.

| Community Profile (Mock) | Value |
| --- | --- |
| Population | 38,500 |
| Median household income | $64,200 |
| Median home value | $238,000 |
| Annual operating budget (General Fund) | $61,950,000 |
| Five-year CIP (all funds) | $61,050,000 |
| Form of government | Council–Manager |
| Service area | Regional hub for surrounding rural communities |

Key message: Strategy must be financially grounded. This document includes a full mock operating forecast, mock department budgets, a mock CIP with funding sources, and performance scorecards.

Executive Summary

This Strategic Plan establishes a five-year framework to guide decision-making, community engagement, and resource alignment.

Engagement approach (mock):

• Governing-body retreat(s) to set priorities and trade-offs

• Leadership workshops to validate operational feasibility

• Staff work sessions to develop cost estimates and timelines

• Stakeholder interviews and surveys to identify service expectations

What makes this plan implementable:

• A five-year operating forecast that shows baseline service costs

• Department-level budgets and staffing assumptions

• A five-year CIP with project cash flows and funding sources

• A performance scorecard linking outcomes to measurable targets

Strategic Priorities (Mock)

Maintain long-term financial sustainability and policy transparency

Invest in infrastructure reinvestment and risk reduction

Improve public safety service reliability and prevention programs

Support managed growth and local economic opportunity

Strengthen organizational capacity, customer service, and performance reporting

1. Planning Approach & Engagement Model

Engagement Philosophy

This plan uses an engagement-driven model that emphasizes shared ownership and transparent decision-making. Engagement is not a single event; it is designed as a sequence of activities that produce documented outputs that feed directly into budgets and implementation plans.

| Engagement Activity | Primary Participants | Output Produced | How It Informs Budget/Implementation |
| --- | --- | --- | --- |
| Governing-body retreat | Council/Board, City Manager, Facilitator | Top priorities; policy trade-offs | Sets service levels and funding assumptions |
| Leadership workshop | Exec team, Dept directors | Operational feasibility check | Refines timelines and staffing impacts |
| Department cost sessions | Finance + Departments | Cost estimates by initiative | Creates budget requests and CIP cash flows |
| Stakeholder interviews | Residents, businesses, institutions | Service expectations and pain points | Shapes KPIs and service delivery changes |
| Public survey/forum | Community-wide | Priority weighting and feedback | Validates trade-offs and communication strategy |

Engagement Timeline (Mock)

| Phase | Weeks | Key Outputs |
| --- | --- | --- |
| Phase 1: Discovery | Weeks 1–4 | Data review, interviews, initial fiscal baseline |
| Phase 2: Retreat Preparation | Weeks 5–6 | Briefing packet, facilitation agenda, scenarios |
| Phase 3: Governing-Body Retreat | Week 7 | Priority outcomes, policy direction |
| Phase 4: Draft Plan + Costing | Weeks 8–12 | Draft plan, initiative costing, draft KPIs |
| Phase 5: Public Review | Weeks 13–14 | Public summary, feedback log, revisions |
| Phase 6: Adoption + Launch | Weeks 15–16 | Council presentation, implementation kickoff |

2. Vision, Mission & Values

Vision

To be a resilient, inclusive, and well-governed community that delivers reliable services and sustainable opportunity for all residents.

Mission

To serve the community through transparent leadership, collaborative planning, and responsible stewardship of public resources.

Core Values (Operationalized)

| Core Value | What It Looks Like in Practice (Mock Examples) |
| --- | --- |
| Accountability | Publish KPIs quarterly; assign initiative owners; document decisions |
| Transparency | Public-facing budget summary; open data dashboards; clear meeting materials |
| Fiscal Responsibility | Multi-year forecasting; reserve policy; lifecycle asset reinvestment |
| Service Excellence | Service standards; customer service training; continuous improvement |
| Inclusion | Multiple engagement channels; language access; targeted outreach |

3. Strategic Planning Principles

These principles govern how priorities are selected and funded:

1) Long-term impacts matter: decisions consider operations, maintenance, and future liabilities.

2) Financial realism: initiatives require a funding plan, not just intent.

3) Operational feasibility: timelines reflect staffing, procurement, and delivery capacity.

4) Performance measurement: outcomes are tracked with clear baselines and targets.

5) Flexibility: annual updates allow the plan to adapt to economic and legislative changes.

| Planning Assumption | Mock Baseline | Planning Range / Sensitivity |
| --- | --- | --- |
| Revenue growth | 2.5–4.5% depending on source | Downside: 1.0%; Upside: 5.5% |
| Inflation | 3.0% baseline | Downside: 2.0%; Upside: 4.5% |
| Salary/benefits growth | 4.0% baseline | Downside: 3.0%; Upside: 5.0% |
| Health insurance trend | 7.5% baseline | Downside: 5.0%; Upside: 10.0% |
| CIP cost escalation | 4.0% baseline | Downside: 2.5%; Upside: 6.0% |

4. Strategic Goal Areas

The plan is organized around seven goal areas. Each goal area includes outcomes, initiatives, funding considerations, and measurable performance indicators.

Governance & Financial Stewardship

Summary (mock): Strengthen financial stewardship, transparency, and governance practices.

Public Safety & Essential Services

Summary (mock): Maintain reliable emergency response, prevention programs, and code enforcement capacity.

Infrastructure & Asset Management

Summary (mock): Prioritize reinvestment and risk reduction through asset management and a funded capital program.

Community Vitality & Economic Opportunity

Summary (mock): Support local businesses, redevelopment, and efficient permitting to encourage investment.

Mobility & Connectivity

Summary (mock): Improve safety and connectivity across streets, sidewalks, and multimodal networks.

Parks, Environment & Quality of Place

Summary (mock): Enhance parks, trails, environmental stewardship, and quality-of-place.

Organizational Excellence & Service Delivery

Summary (mock): Invest in people, processes, and technology to deliver consistent service excellence.

5. Strategic Outcomes

| Outcome | What Success Looks Like (Mock) | Primary Measures |
| --- | --- | --- |
| Financial sustainability | Balanced operating forecast with reserve policy met | Fund balance %, audit findings |
| Reliable core services | Stable response times and regulatory compliance | Response time KPIs, compliance rates |
| Infrastructure reinvestment | Improved condition indices and fewer failures | PCI, breaks per 100 miles |
| Economic vitality | Improved permitting cycle time and job growth | Jobs, occupancy, permit cycle time |
| Mobility & safety | Reduced fatalities and closed network gaps | Fatalities, sidewalk miles closed |
| Quality of place | Higher satisfaction and improved environmental indicators | Satisfaction %, canopy coverage |
| Organizational excellence | Higher engagement and better customer service | Engagement score, first-contact resolution |

Financial & Operational Trends (Charts – Mock)

The following charts illustrate the plan’s integrated financial and operational assumptions. (Charts use default plotting styles; no brand-specific colors are required for procurement submissions.)

6. Engagement-Focused Strategic Initiatives

Governance & Financial Stewardship

| ID | Initiative (Mock) | Timing | Primary Funding | 5-Yr Cost (Est.) | Owner |
| --- | --- | --- | --- | --- | --- |
| SI-001 | Initiative 1: Governance program enhancement | Year 2–3 | Mixed Sources | $400,000 | Finance |
| SI-002 | Initiative 2: Governance program enhancement | Year 1–2 | Utility Fund | $650,000 | Fire |
| SI-003 | Initiative 3: Governance program enhancement | Year 2–3 | Grant/Intergov. | $250,000 | Planning |
| SI-004 | Initiative 4: Governance program enhancement | Year 1–2 | Utility Fund | $650,000 | IT |
| SI-005 | Initiative 5: Governance program enhancement | Year 3–5 | Utility Fund | $650,000 | Planning |
| SI-006 | Initiative 6: Governance program enhancement | Year 3–5 | Grant/Intergov. | $1,100,000 | Parks |

Engagement notes (mock): Each initiative will be reviewed annually with the governing body and refined through stakeholder feedback, department work sessions, and budget prioritization workshops.

Public Safety & Essential Services

| ID | Initiative (Mock) | Timing | Primary Funding | 5-Yr Cost (Est.) | Owner |
| --- | --- | --- | --- | --- | --- |
| SI-007 | Initiative 7: Public Safety program enhancement | Year 1–5 | Utility Fund | $1,800,000 | Public Works |
| SI-008 | Initiative 8: Public Safety program enhancement | Year 2–3 | Utility Fund | $150,000 | Police |
| SI-009 | Initiative 9: Public Safety program enhancement | Year 2–3 | General Fund | $1,800,000 | IT |
| SI-010 | Initiative 10: Public Safety program enhancement | Year 2–3 | Capital Fund | $1,100,000 | Fire |
| SI-011 | Initiative 11: Public Safety program enhancement | Year 2–3 | Grant/Intergov. | $150,000 | Parks |
| SI-012 | Initiative 12: Public Safety program enhancement | Year 3–5 | Utility Fund | $1,100,000 | City Manager Office |

Engagement notes (mock): Each initiative will be reviewed annually with the governing body and refined through stakeholder feedback, department work sessions, and budget prioritization workshops.

Infrastructure & Asset Management

| ID | Initiative (Mock) | Timing | Primary Funding | 5-Yr Cost (Est.) | Owner |
| --- | --- | --- | --- | --- | --- |
| SI-013 | Initiative 13: Infrastructure program enhancement | Year 1–5 | Grant/Intergov. | $650,000 | Planning |
| SI-014 | Initiative 14: Infrastructure program enhancement | Year 1–2 | Grant/Intergov. | $650,000 | Planning |
| SI-015 | Initiative 15: Infrastructure program enhancement | Year 2–3 | General Fund | $150,000 | Police |
| SI-016 | Initiative 16: Infrastructure program enhancement | Year 2–3 | General Fund | $650,000 | Parks |
| SI-017 | Initiative 17: Infrastructure program enhancement | Year 1–2 | General Fund | $1,100,000 | City Manager Office |
| SI-018 | Initiative 18: Infrastructure program enhancement | Year 2–3 | Mixed Sources | $1,100,000 | Finance |

Engagement notes (mock): Each initiative will be reviewed annually with the governing body and refined through stakeholder feedback, department work sessions, and budget prioritization workshops.

Community Vitality & Economic Opportunity

| ID | Initiative (Mock) | Timing | Primary Funding | 5-Yr Cost (Est.) | Owner |
| --- | --- | --- | --- | --- | --- |
| SI-019 | Initiative 19: Community Vitality program enhancement | Year 1–2 | General Fund | $400,000 | Police |
| SI-020 | Initiative 20: Community Vitality program enhancement | Year 1–5 | Utility Fund | $1,100,000 | Fire |
| SI-021 | Initiative 21: Community Vitality program enhancement | Year 3–5 | Grant/Intergov. | $400,000 | Finance |
| SI-022 | Initiative 22: Community Vitality program enhancement | Year 1–5 | Grant/Intergov. | $150,000 | IT |
| SI-023 | Initiative 23: Community Vitality program enhancement | Year 3–5 | General Fund | $650,000 | Public Works |
| SI-024 | Initiative 24: Community Vitality program enhancement | Year 3–5 | Capital Fund | $150,000 | IT |

Engagement notes (mock): Each initiative will be reviewed annually with the governing body and refined through stakeholder feedback, department work sessions, and budget prioritization workshops.

Mobility & Connectivity

| ID | Initiative (Mock) | Timing | Primary Funding | 5-Yr Cost (Est.) | Owner |
| --- | --- | --- | --- | --- | --- |
| SI-025 | Initiative 25: Mobility program enhancement | Year 2–3 | Mixed Sources | $1,800,000 | City Manager Office |
| SI-026 | Initiative 26: Mobility program enhancement | Year 3–5 | Utility Fund | $250,000 | City Manager Office |
| SI-027 | Initiative 27: Mobility program enhancement | Year 3–5 | General Fund | $1,100,000 | Fire |
| SI-028 | Initiative 28: Mobility program enhancement | Year 3–5 | Utility Fund | $1,100,000 | Parks |
| SI-029 | Initiative 29: Mobility program enhancement | Year 3–5 | Utility Fund | $250,000 | Police |
| SI-030 | Initiative 30: Mobility program enhancement | Year 1–5 | Utility Fund | $250,000 | Police |

Engagement notes (mock): Each initiative will be reviewed annually with the governing body and refined through stakeholder feedback, department work sessions, and budget prioritization workshops.

Parks, Environment & Quality of Place

| ID | Initiative (Mock) | Timing | Primary Funding | 5-Yr Cost (Est.) | Owner |
| --- | --- | --- | --- | --- | --- |
| SI-031 | Initiative 31: Parks, Environment program enhancement | Year 1–5 | Capital Fund | $1,100,000 | City Manager Office |
| SI-032 | Initiative 32: Parks, Environment program enhancement | Year 3–5 | Grant/Intergov. | $150,000 | Fire |
| SI-033 | Initiative 33: Parks, Environment program enhancement | Year 3–5 | Grant/Intergov. | $250,000 | Parks |
| SI-034 | Initiative 34: Parks, Environment program enhancement | Year 1–2 | Utility Fund | $400,000 | Finance |
| SI-035 | Initiative 35: Parks, Environment program enhancement | Year 1–5 | Utility Fund | $250,000 | Parks |
| SI-036 | Initiative 36: Parks, Environment program enhancement | Year 1–5 | Mixed Sources | $250,000 | City Manager Office |

Engagement notes (mock): Each initiative will be reviewed annually with the governing body and refined through stakeholder feedback, department work sessions, and budget prioritization workshops.

Organizational Excellence & Service Delivery

| ID | Initiative (Mock) | Timing | Primary Funding | 5-Yr Cost (Est.) | Owner |
| --- | --- | --- | --- | --- | --- |
| SI-037 | Initiative 37: Organizational Excellence program enhancement | Year 3–5 | General Fund | $650,000 | Finance |
| SI-038 | Initiative 38: Organizational Excellence program enhancement | Year 2–3 | Grant/Intergov. | $650,000 | Public Works |
| SI-039 | Initiative 39: Organizational Excellence program enhancement | Year 3–5 | General Fund | $650,000 | Planning |
| SI-040 | Initiative 40: Organizational Excellence program enhancement | Year 1–5 | General Fund | $650,000 | Public Works |
| SI-041 | Initiative 41: Organizational Excellence program enhancement | Year 2–3 | General Fund | $250,000 | Public Works |
| SI-042 | Initiative 42: Organizational Excellence program enhancement | Year 1–5 | Utility Fund | $1,100,000 | IT |

Engagement notes (mock): Each initiative will be reviewed annually with the governing body and refined through stakeholder feedback, department work sessions, and budget prioritization workshops.

7. Implementation & Accountability

Implementation Governance (Mock)

Implementation is managed through an annual action plan, quarterly performance reporting, and an accountability structure that assigns an owner to each initiative.

Governance structure (mock):

• Governing body: annual strategic check-in and priority confirmation

• Executive leadership: monthly progress review and risk escalation

• Department owners: initiative delivery and KPI reporting

• Finance: budget integration, forecasting, and quarterly public summaries

Annual Action Plan (Sample – Year 1)

| Initiative ID | Initiative | Timing | Owner | Funding | Cost | Status |
| --- | --- | --- | --- | --- | --- | --- |
| SI-001 | Initiative 1: Governance program enhancement... | Year 2–3 | Finance | Mixed Sources | $400,000 | In Progress |
| SI-002 | Initiative 2: Governance program enhancement... | Year 1–2 | Fire | Utility Fund | $650,000 | In Progress |
| SI-003 | Initiative 3: Governance program enhancement... | Year 2–3 | Planning | Grant/Intergov. | $250,000 | In Progress |
| SI-004 | Initiative 4: Governance program enhancement... | Year 1–2 | IT | Utility Fund | $650,000 | In Progress |
| SI-005 | Initiative 5: Governance program enhancement... | Year 3–5 | Planning | Utility Fund | $650,000 | In Progress |
| SI-006 | Initiative 6: Governance program enhancement... | Year 3–5 | Parks | Grant/Intergov. | $1,100,000 | In Progress |
| SI-007 | Initiative 7: Public Safety program enhanceme... | Year 1–5 | Public Works | Utility Fund | $1,800,000 | In Progress |
| SI-008 | Initiative 8: Public Safety program enhanceme... | Year 2–3 | Police | Utility Fund | $150,000 | In Progress |
| SI-009 | Initiative 9: Public Safety program enhanceme... | Year 2–3 | IT | General Fund | $1,800,000 | In Progress |
| SI-010 | Initiative 10: Public Safety program enhancem... | Year 2–3 | Fire | Capital Fund | $1,100,000 | In Progress |
| SI-011 | Initiative 11: Public Safety program enhancem... | Year 2–3 | Parks | Grant/Intergov. | $150,000 | In Progress |
| SI-012 | Initiative 12: Public Safety program enhancem... | Year 3–5 | City Manager Office | Utility Fund | $1,100,000 | In Progress |
| SI-013 | Initiative 13: Infrastructure program enhance... | Year 1–5 | Planning | Grant/Intergov. | $650,000 | In Progress |
| SI-014 | Initiative 14: Infrastructure program enhance... | Year 1–2 | Planning | Grant/Intergov. | $650,000 | In Progress |

Quarterly Reporting Calendar (Mock)

| Quarter | Primary Deliverables | Decision Points |
| --- | --- | --- |
| Q1 | Baseline KPI update; budget assumptions refresh | Confirm policy trade-offs and risks |
| Q2 | Mid-year financial forecast; CIP cash flow update | Adjust project sequencing as needed |
| Q3 | Budget development workshops; initiative reprioritization | Approve draft budget priorities |
| Q4 | Year-end KPI report; annual action plan refresh | Adopt next-year action plan and budget |

Risk Register (Mock)

| Risk | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Revenue volatility | Medium | High | Conservative forecasting; contingency reserve; quarterly monitoring |
| Construction cost escalation | High | Medium | Escalation assumptions; bid alternates; phased delivery |
| Staffing/retention challenges | Medium | High | Compensation review; training; recruitment pipeline |
| Aging infrastructure failures | Medium | High | Asset management; preventive maintenance; prioritized CIP |
| Grant dependency | Low | Medium | Diversify funding; maintain compliance; early application planning |

8. Financial & Budget Alignment

This section includes a full five-year operating forecast, department budgets, staffing plan, and a capital improvement program with funding sources and cash flows.

Budget Summary One-Pager (Council Packet Style – Mock)

| Year | Total Revenues | Total Expenditures | Net | Ending Fund Balance |
| --- | --- | --- | --- | --- |
| Year 1 | $61,950,000 | $48,550,000 | $13,400,000 | $31,150,000 |
| Year 2 | $64,185,000 | $50,272,100 | $13,912,900 | $44,612,900 |
| Year 3 | $66,506,139 | $52,056,784 | $14,449,355 | $58,312,255 |
| Year 4 | $68,916,880 | $53,906,372 | $15,010,508 | $72,872,763 |
| Year 5 | $71,420,825 | $55,823,265 | $15,597,560 | $88,020,323 |

Policy note (mock): Maintain unassigned fund balance at or above 25% of General Fund expenditures.

Five-Year Operating Forecast – Revenues (Detail)

| Revenue Source | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| --- | --- | --- | --- | --- | --- |
| Property Tax | $26,500,000 | $27,692,500 | $28,938,662 | $30,240,902 | $31,601,743 |
| Sales Tax | $16,200,000 | $16,767,000 | $17,353,845 | $17,961,230 | $18,589,873 |
| Franchise Fees | $3,200,000 | $3,280,000 | $3,362,000 | $3,446,050 | $3,532,201 |
| Licenses & Permits | $1,650,000 | $1,699,500 | $1,750,485 | $1,803,000 | $1,857,090 |
| Charges for Services | $8,750,000 | $9,012,500 | $9,282,875 | $9,561,361 | $9,848,202 |
| Fines & Forfeitures | $900,000 | $909,000 | $918,090 | $927,271 | $936,544 |
| Intergovernmental | $4,100,000 | $4,161,500 | $4,223,922 | $4,287,281 | $4,351,591 |
| Interest/Other | $650,000 | $663,000 | $676,260 | $689,785 | $703,581 |
| TOTAL | $61,950,000 | $64,185,000 | $66,506,139 | $68,916,880 | $71,420,825 |

Assumptions (mock): property tax reflects new value growth and modest rate stability; sales tax reflects regional retail capture; charges for services grow with volume and CPI adjustments.

Five-Year Operating Forecast – Expenditures (Detail)

| Expenditure Function | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| --- | --- | --- | --- | --- | --- |
| Police | $15,900,000 | $16,536,000 | $17,197,440 | $17,885,338 | $18,600,751 |
| Fire & EMS | $9,750,000 | $10,140,000 | $10,545,600 | $10,967,424 | $11,406,121 |
| Public Works | $6,300,000 | $6,520,500 | $6,748,717 | $6,984,923 | $7,229,395 |
| Utilities (Ops Support) | $2,950,000 | $3,038,500 | $3,129,655 | $3,223,545 | $3,320,251 |
| Parks & Recreation | $3,150,000 | $3,244,500 | $3,341,835 | $3,442,090 | $3,545,353 |
| Library & Community Services | $1,450,000 | $1,490,600 | $1,532,337 | $1,575,242 | $1,619,349 |
| General Government | $5,600,000 | $5,768,000 | $5,941,040 | $6,119,271 | $6,302,849 |
| Information Technology | $1,250,000 | $1,290,000 | $1,331,280 | $1,373,881 | $1,417,845 |
| Debt Service (GF share) | $2,200,000 | $2,244,000 | $2,288,880 | $2,334,658 | $2,381,351 |
| TOTAL | $48,550,000 | $50,272,100 | $52,056,784 | $53,906,372 | $55,823,265 |

Assumptions (mock): salary and benefits reflect market pressures; public safety staffing phased; technology refresh included; debt service reflects amortization schedule.

Fund Balance Policy & Five-Year Projection (Mock)

| Year | Beginning Fund Balance | Net Change | Ending Fund Balance |
| --- | --- | --- | --- |
| Year 1 | $18,500,000 | $12,650,000 | $31,150,000 |
| Year 2 | $31,150,000 | $13,462,900 | $44,612,900 |
| Year 3 | $44,612,900 | $13,699,355 | $58,312,255 |
| Year 4 | $58,312,255 | $14,560,508 | $72,872,763 |
| Year 5 | $72,872,763 | $15,147,560 | $88,020,323 |

Reserve policy (mock): unassigned fund balance >= 25% of annual General Fund expenditures; separate emergency reserve target >= 5% of expenditures.

Department Budgets (Mock) – Operating

| Department | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| --- | --- | --- | --- | --- | --- |
| Police | $15,900,000 | $16,536,000 | $17,197,440 | $17,885,338 | $18,600,751 |
| Fire & EMS | $9,750,000 | $10,140,000 | $10,545,600 | $10,967,424 | $11,406,121 |
| Public Works | $6,300,000 | $6,520,500 | $6,748,717 | $6,984,923 | $7,229,395 |
| Parks & Recreation | $3,150,000 | $3,244,500 | $3,341,835 | $3,442,090 | $3,545,353 |
| Library & Community Services | $1,450,000 | $1,490,600 | $1,532,337 | $1,575,242 | $1,619,349 |
| General Government | $5,600,000 | $5,768,000 | $5,941,040 | $6,119,271 | $6,302,849 |
| Information Technology | $1,250,000 | $1,290,000 | $1,331,280 | $1,373,881 | $1,417,845 |

Note (mock): Department budgets include personnel, operating, and contractual services. Capital outlays are shown in the CIP section.

Staffing Plan (FTE) – Five-Year (Mock)

| Department | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| --- | --- | --- | --- | --- | --- |
| Police | 92 | 92 | 94 | 92 | 94 |
| Fire & EMS | 58 | 58 | 60 | 58 | 60 |
| Public Works | 44 | 45 | 44 | 45 | 44 |
| Parks & Recreation | 22 | 22 | 22 | 22 | 23 |
| Library & Community Services | 10 | 10 | 10 | 10 | 10 |
| Administration/Finance/HR | 26 | 26 | 26 | 26 | 26 |
| IT | 8 | 8 | 8 | 8 | 8 |
| TOTAL | 260 | 261 | 264 | 261 | 265 |

Workforce assumptions (mock): limited growth in public safety and public works; operational efficiency and technology modernization reduce administrative growth needs.

9. Ongoing Review & Engagement

The plan is maintained as a living framework through annual progress reviews, mid-cycle adjustments, and continuous community engagement.

Annual review (mock):

• Refresh forecast assumptions and update reserve targets

• Reprioritize initiatives based on performance and capacity

• Update CIP project sequencing based on funding and readiness

• Publish an annual progress report with updated dashboards

| Review Type | Frequency | Primary Outputs |
| --- | --- | --- |
| Quarterly performance review | Quarterly | KPI dashboard update; risk log refresh |
| Mid-year financial forecast | Semi-annual | Updated revenue/expenditure projections |
| Annual action plan refresh | Annual | Next-year priorities; initiative owner assignments |
| Full strategic refresh | Every 3–5 years | Updated goals, priorities, community needs assessment |

10. Conclusion

This demonstration plan shows how an engagement-driven strategic plan can be connected to real implementation tools: a multi-year budget forecast, department budgets, a capital improvement program, and measurable performance targets.

Key takeaway: Strategy becomes executable when it is tied to dollars, staffing, timelines, and accountability.

Appendix A: Facilitated Retreat Agenda & Materials (Mock)

One-Day Governing-Body Retreat Agenda

| Time | Session | Purpose | Output |
| --- | --- | --- | --- |
| 8:30–9:00 | Welcome & norms | Set expectations and rules | Agreed norms |
| 9:00–10:15 | Current-state briefing | Review fiscal & service baseline | Shared understanding |
| 10:30–12:00 | Strategic landscape & SWOT | Identify risks/opportunities | SWOT summary |
| 1:00–2:30 | Priority setting & trade-offs | Select top outcomes | Priority list |
| 2:45–4:00 | Budget alignment scenarios | Link priorities to resources | Scenario direction |
| 4:00–4:30 | Wrap-up & next steps | Confirm deliverables | Action items |

Retreat Materials (Mock)

Briefing packet: fiscal snapshot, service dashboards, capital needs summary

Engagement summary: survey results, stakeholder themes, priority ranking

Decision worksheets: trade-off scenarios and funding options

Draft outcomes map: goals → initiatives → measures

Appendix B: Stakeholder Engagement Map & Communications Plan (Mock)

| Stakeholder Group | Engagement Method | Frequency | Key Topics |
| --- | --- | --- | --- |
| Residents | Survey + public forum | 2–3 times/year | Priorities, service expectations, trade-offs |
| Business community | Roundtables | Semi-annual | Permitting, infrastructure, workforce |
| Regional partners | Coordination meetings | Quarterly | Transportation, grants, emergency mgmt |
| Employees | Pulse surveys + workshops | Quarterly | Process improvement, training needs |
| Institutions (schools/healthcare) | Interviews | Annual | Joint planning and capacity |

Public Communications Cadence (Mock)

| Communication Product | Audience | Frequency | Owner |
| --- | --- | --- | --- |
| Quarterly dashboard update | Public + Council | Quarterly | Performance Office/Finance |
| Budget-in-brief | Public | Annual | Finance |
| Capital project map update | Public | Quarterly | Public Works |
| Annual progress report | Public + Council | Annual | City Manager Office |

Appendix C: Five-Year Operating Forecast (Detail)

Revenue Assumptions (Mock)

| Revenue Source | Baseline | Annual Growth Assumption | Primary Drivers |
| --- | --- | --- | --- |
| Property Tax | $26,500,000 | 4.5% | Volume, CPI, local economic base |
| Sales Tax | $16,200,000 | 3.5% | Volume, CPI, local economic base |
| Franchise Fees | $3,200,000 | 2.5% | Volume, CPI, local economic base |
| Licenses & Permits | $1,650,000 | 3.0% | Volume, CPI, local economic base |
| Charges for Services | $8,750,000 | 3.0% | Volume, CPI, local economic base |
| Fines & Forfeitures | $900,000 | 1.0% | Volume, CPI, local economic base |
| Intergovernmental | $4,100,000 | 1.5% | Volume, CPI, local economic base |
| Interest/Other | $650,000 | 2.0% | Volume, CPI, local economic base |

Expenditure Assumptions (Mock)

| Expenditure Function | Baseline | Annual Growth Assumption | Primary Drivers |
| --- | --- | --- | --- |
| Police | $15,900,000 | 4.0% | Personnel, inflation, service demand |
| Fire & EMS | $9,750,000 | 4.0% | Personnel, inflation, service demand |
| Public Works | $6,300,000 | 3.5% | Personnel, inflation, service demand |
| Utilities (Ops Support) | $2,950,000 | 3.0% | Personnel, inflation, service demand |
| Parks & Recreation | $3,150,000 | 3.0% | Personnel, inflation, service demand |
| Library & Community Services | $1,450,000 | 2.8% | Personnel, inflation, service demand |
| General Government | $5,600,000 | 3.0% | Personnel, inflation, service demand |
| Information Technology | $1,250,000 | 3.2% | Personnel, inflation, service demand |
| Debt Service (GF share) | $2,200,000 | 2.0% | Personnel, inflation, service demand |

Appendix D: Department Budgets & Staffing Plan (Mock)

Department Budget Detail – Year 1 (Mock)

| Department | Category | Year 1 Cost | Notes |
| --- | --- | --- | --- |
| Police | Personnel | $12,200,000 | 92 FTE; wage/benefit baseline |
| Police | Operating | $2,150,000 | Fuel, supplies, training |
| Police | Contractual | $1,050,000 | Dispatch/records support |
| Fire & EMS | Personnel | $7,200,000 | 58 FTE; overtime management |
| Fire & EMS | Operating | $1,150,000 | Medical supplies, apparatus maint. |
| Public Works | Personnel | $3,250,000 | 44 FTE; crew coverage |
| Public Works | Operating | $2,150,000 | Materials, fleet, utilities |
| Parks & Recreation | Personnel | $1,550,000 | Seasonal + full time |
| Parks & Recreation | Operating | $1,200,000 | Programs, facilities |
| General Government | Personnel | $3,400,000 | Admin/finance/HR |
| General Government | Operating | $1,250,000 | Professional services |
| IT | Operating | $1,250,000 | Security, licensing, support |

Training & Workforce Development Plan (Mock)

| Program | Target Group | Annual Hours | Outcome |
| --- | --- | --- | --- |
| Supervisor academy | New supervisors | 24 | Improved coaching and retention |
| Customer service training | All staff | 8 | Higher first-contact resolution |
| Cybersecurity awareness | All users | 4 | Reduced phishing risk |
| Public safety specialty training | Police/Fire | 40 | Improved readiness and compliance |

Appendix E: Five-Year Capital Improvement Program (Projects, Funding, Cash Flow)

CIP Project List (Mock)

| Project ID | Category | Project Name | Planned Year | Cost | Funding Source |
| --- | --- | --- | --- | --- | --- |
| CIP-01 | Facilities | Project 1 – Facilities enhancement | Year 2 | $1,800,000 | Pay-as-you-go |
| CIP-02 | Streets & Drainage | Project 2 – Streets & Drainage enhancement | Year 5 | $650,000 | Revenue Bonds |
| CIP-03 | Parks & Trails | Project 3 – Parks & Trails enhancement | Year 1 | $2,500,000 | Certificates of Obligation |
| CIP-04 | Streets & Drainage | Project 4 – Streets & Drainage enhancement | Year 1 | $1,800,000 | Grants |
| CIP-05 | Streets & Drainage | Project 5 – Streets & Drainage enhancement | Year 2 | $650,000 | Impact Fees |
| CIP-06 | Public Safety | Project 6 – Public Safety enhancement | Year 1 | $5,000,000 | Impact Fees |
| CIP-07 | Streets & Drainage | Project 7 – Streets & Drainage enhancement | Year 2 | $3,750,000 | Impact Fees |
| CIP-08 | Streets & Drainage | Project 8 – Streets & Drainage enhancement | Year 5 | $2,500,000 | Grants |
| CIP-09 | Streets & Drainage | Project 9 – Streets & Drainage enhancement | Year 2 | $650,000 | Impact Fees |
| CIP-10 | Water/Wastewater | Project 10 – Water/Wastewater enhancement | Year 3 | $1,800,000 | Certificates of Obligation |
| CIP-11 | Parks & Trails | Project 11 – Parks & Trails enhancement | Year 1 | $2,500,000 | Revenue Bonds |
| CIP-12 | Parks & Trails | Project 12 – Parks & Trails enhancement | Year 2 | $650,000 | Impact Fees |
| CIP-13 | Parks & Trails | Project 13 – Parks & Trails enhancement | Year 2 | $1,200,000 | Pay-as-you-go |
| CIP-14 | Parks & Trails | Project 14 – Parks & Trails enhancement | Year 1 | $2,500,000 | Pay-as-you-go |
| CIP-15 | Parks & Trails | Project 15 – Parks & Trails enhancement | Year 2 | $1,800,000 | Impact Fees |
| CIP-16 | Public Safety | Project 16 – Public Safety enhancement | Year 3 | $1,800,000 | Impact Fees |
| CIP-17 | Public Safety | Project 17 – Public Safety enhancement | Year 3 | $1,200,000 | Certificates of Obligation |
| CIP-18 | Water/Wastewater | Project 18 – Water/Wastewater enhancement | Year 2 | $650,000 | Impact Fees |

CIP Project List (Mock) – Continued

| Project ID | Category | Project Name | Planned Year | Cost | Funding Source |
| --- | --- | --- | --- | --- | --- |
| CIP-19 | Facilities | Project 19 – Facilities enhancement | Year 5 | $1,800,000 | Revenue Bonds |
| CIP-20 | Technology | Project 20 – Technology enhancement | Year 4 | $1,200,000 | Impact Fees |
| CIP-21 | Streets & Drainage | Project 21 – Streets & Drainage enhancement | Year 1 | $2,500,000 | Grants |
| CIP-22 | Water/Wastewater | Project 22 – Water/Wastewater enhancement | Year 3 | $900,000 | Grants |
| CIP-23 | Public Safety | Project 23 – Public Safety enhancement | Year 1 | $3,750,000 | Pay-as-you-go |
| CIP-24 | Parks & Trails | Project 24 – Parks & Trails enhancement | Year 5 | $5,000,000 | Revenue Bonds |
| CIP-25 | Facilities | Project 25 – Facilities enhancement | Year 3 | $2,500,000 | Grants |
| CIP-26 | Parks & Trails | Project 26 – Parks & Trails enhancement | Year 4 | $650,000 | Pay-as-you-go |
| CIP-27 | Facilities | Project 27 – Facilities enhancement | Year 4 | $3,750,000 | Pay-as-you-go |
| CIP-28 | Streets & Drainage | Project 28 – Streets & Drainage enhancement | Year 3 | $3,750,000 | Impact Fees |
| CIP-29 | Technology | Project 29 – Technology enhancement | Year 4 | $1,200,000 | Grants |
| CIP-30 | Technology | Project 30 – Technology enhancement | Year 3 | $650,000 | Grants |

CIP Cash Flow by Year (Mock)

| Year | CIP Spending (All Categories) |
| --- | --- |
| Year 1 | $20,550,000 |
| Year 2 | $11,150,000 |
| Year 3 | $12,600,000 |
| Year 4 | $6,800,000 |
| Year 5 | $9,950,000 |

Appendix F: Debt & Fund Balance Policy Exhibits (Mock)

Debt Service Schedule (General Fund Share – Mock)

| Year | Principal | Interest | Total Debt Service |
| --- | --- | --- | --- |
| Year 1 | $2,533,333 | $1,425,000 | $3,958,333 |
| Year 2 | $2,533,333 | $1,330,000 | $3,863,333 |
| Year 3 | $2,533,333 | $1,235,000 | $3,768,333 |
| Year 4 | $2,533,333 | $1,140,000 | $3,673,333 |
| Year 5 | $2,533,333 | $1,045,000 | $3,578,333 |

Fund Balance Policy (Mock)

Policy targets (mock):

• Unassigned fund balance: ≥ 25% of annual General Fund expenditures

• Emergency reserve: ≥ 5% of annual General Fund expenditures

• Stabilization reserve: 2–4% of annual expenditures for economic volatility

• One-time revenues: dedicated to capital or reserve replenishment

Appendix G: Performance Scorecards & Dashboard Mockups (Mock)

The following scorecards provide baselines and five-year targets. These measures are designed to be understandable to the public and actionable by departments.

Governance & Financial Stewardship

| Measure | Unit | Baseline | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Budget adopted on time | Yes/No | Yes | Yes | Yes | Yes | Yes | Yes |
| Unassigned fund balance (% of GF exp.) | % | 28% | 28% | 29% | 30% | 30% | 31% |
| Audit findings | Count | 2 | 2 | 1 | 1 | 0 | 0 |
| Capital plan published | Yes/No | Yes | Yes | Yes | Yes | Yes | Yes |
| Procurement cycle time | Days | 42 | 42 | 40 | 38 | 36 | 35 |

Public Safety & Essential Services

| Measure | Unit | Baseline | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Police priority response time | Minutes | 7.8 | 7.8 | 7.6 | 7.4 | 7.3 | 7.2 |
| Fire first-due turnout+travel (90th pct.) | Minutes | 9.5 | 9.5 | 9.3 | 9.2 | 9.0 | 9.0 |
| Code compliance cases resolved <30 days | % | 62% | 62% | 66% | 70% | 72% | 75% |
| Community risk reduction events | Count | 18 | 18 | 20 | 22 | 24 | 26 |
| Officer training completion | % | 94% | 94% | 95% | 96% | 97% | 97% |

Infrastructure & Asset Management

| Measure | Unit | Baseline | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Pavement condition index | Index | 66 | 66 | 68 | 70 | 71 | 73 |
| Water main breaks per 100 miles | Count | 18 | 18 | 17 | 16 | 15 | 14 |
| Preventive maintenance compliance | % | 72% | 72% | 76% | 80% | 82% | 85% |
| CIP on-time/on-budget projects | % | 78% | 78% | 80% | 82% | 84% | 85% |
| Stormwater hot-spot mitigations | Count | 6 | 6 | 8 | 9 | 10 | 12 |

Community Vitality & Economic Opportunity

| Measure | Unit | Baseline | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Net new jobs (annual) | Count | 240 | 240 | 260 | 285 | 300 | 320 |
| Commercial occupancy | % | 89% | 89% | 90% | 91% | 92% | 93% |
| Small business assistance engagements | Count | 40 | 40 | 55 | 65 | 70 | 75 |
| Permitting cycle time (median) | Days | 18 | 18 | 17 | 16 | 15 | 14 |
| Downtown foot traffic index | Index | 100 | 100 | 104 | 108 | 112 | 115 |

Mobility & Connectivity

| Measure | Unit | Baseline | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Traffic fatalities (annual) | Count | 6 | 6 | 5 | 5 | 4 | 4 |
| Sidewalk gap miles closed | Miles | 1.2 | 1.2 | 1.8 | 2.2 | 2.8 | 3.4 |
| Bicycle network miles added | Miles | 0.8 | 0.8 | 1.2 | 1.6 | 2.0 | 2.4 |
| Transit/partner coordination meetings | Count | 10 | 10 | 12 | 12 | 14 | 14 |
| Work-zone complaints resolved <7 days | % | 70% | 70% | 74% | 78% | 82% | 85% |

Parks, Environment & Quality of Place

| Measure | Unit | Baseline | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Park acres per 1,000 residents | Acres | 8.1 | 8.1 | 8.2 | 8.3 | 8.4 | 8.6 |
| Trail miles maintained to standard | % | 76% | 76% | 80% | 83% | 86% | 88% |
| Tree canopy coverage | % | 24% | 24% | 24.5% | 25% | 25.5% | 26% |
| Litter index score (lower=better) | Score | 3.4 | 3.4 | 3.2 | 3.0 | 2.9 | 2.8 |
| Recreation program satisfaction | % | 88% | 88% | 89% | 90% | 91% | 92% |

Organizational Excellence & Service Delivery

| Measure | Unit | Baseline | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Employee engagement score | Score | 72 | 72 | 74 | 76 | 78 | 79 |
| Annual training hours per employee | Hours | 18 | 18 | 20 | 22 | 24 | 24 |
| Customer service first-contact resolution | % | 64% | 64% | 68% | 72% | 75% | 78% |
| IT system uptime | % | 99.2% | 99.2% | 99.3% | 99.4% | 99.5% | 99.5% |
| Open data dashboard updates | Per year | 6 | 6 | 8 | 10 | 12 | 12 |

Implementation Dashboard (Mock – One Page)

| Area | What We Track | Reporting |
| --- | --- | --- |
| Budget | Forecast vs. actual; reserve status; revenue volatility | Quarterly |
| CIP | Schedule, cost, funding source readiness | Quarterly |
| Service KPIs | Response times, condition indices, satisfaction measures | Quarterly |
| Workforce | Vacancy rates, training completion, engagement score | Semi-annual |
| Engagement | Public updates, forums, surveys, feedback logs | Annual |

End of Demonstration Plan. All content is fictional and intended solely for illustrative purposes.