## Slide 1
Gorakshya Hydropower Limited Kathmandu -9, Battisputali

## Slide 3: Progress on Headwork / Intake
Particulars | Progress %
Flood Wall | 100%
Weir | 95%
Under sluice | 95%
Gravel Trap | 75%
Settling Basin | 45%
Total | 82%

## Slide 4: Progress on Hydro Mechanical Intake
Particulars | Particulars | Progress %
Undersluice | Stop Log Frame | 100%
 | Main Gate Frame | 100%
Trash Passage | Stop Log Frame | 100%
 | Main Gate Frame | 100%
Gravel Trap | Intake Gate Frame | 100%
Settling Basin | Inlet Seal Beam | 100%
 | Inlet Seal Gate | 50%
 | Inlet Vertical Gate Frame | 50%
Total |  | 88%

## Slide 5
Headworks

## Slide 6
Headworks

## Slide 7: Weir

## Slide 8: Weir

## Slide 9: Concrete Casting at Weir

## Slide 10: Concrete Casting at Weir

## Slide 11: Concrete Casting at Weir

## Slide 12
Under Sluice (River Diversion)

## Slide 13: Gravel Trap

## Slide 14: Gravel Trap

## Slide 15: Settling Basin

## Slide 16: Settling Basin

## Slide 17: Settling Basin

## Slide 18
Flood Wall for Head Work

## Slide 19
Flood Wall for Head Work

## Slide 20: Progress on Tunnel
Tunnel Progress:
Particulars | Progress (in Mtr)
Inlet to Adit | 1,045 mtr.
Adit Upstream towards Inlet | 425 mtr.
Adit Downstream towards Outlet | 385 mtr.
T Junction from Adit (upstream and Down stream) | 188 mtr.
Total | 2,043 mtr.
Total tunnel length | 3,590 mtr.
Progress % | 56.91%

## Slide 21
Inlet Portal
Notes: 1000+

## Slide 22
Inlet Tunnel

## Slide 23
Inlet Tunnel Circuiting

## Slide 24
Adit Tunnel

## Slide 25
Adit Junction
Notes: Upstream 300 and down stream 300 + 188 for T structure

## Slide 26
Adit Tunnel
Notes: Upstream 300 and down stream 300 + 188 for T structure

## Slide 27: Progress on Powerhouse
Powerhouse Progress:
Particulars | Progress (in %)
Powerhouse portal excavation | 100%
Main Access Tunnel excavation | 10%
Tailrace Tunnel excavation | 45%
Tailrace Excavation | 100%
Tailrace Gate Frame | 100%
Tailrace culvert | 75%
Power House Flood Wall | 100%

## Slide 28
MAT and Tailrace Tunnel

## Slide 29
Powerhouse Main Access Tunnel

## Slide 30
Tailrace Tunnel

## Slide 31
Tailrace Tunnel

## Slide 32
Tailrace Excavation

## Slide 33
Tailrace Excavation

## Slide 34: Tail Race

## Slide 35: Tail Race End

## Slide 36: Powerhouse Flood Wall

## Slide 37
Site Office

## Slide 38
Financial Progress

## Slide 39: Financial Progress (in Crore)
Chart: 
| Budget | Expenses
Financial Progress (in Crore) | 486.2904 | 241.9889

## Slide 40: Financial Vs Physical Progress
Chart: 
Chart: 
Chart: 
| Financial Progress | Physical Progress
 | 0.49762 | 0.63377

## Slide 41: Loan Utilization (Amt in Cr.)
Chart: 
| Loan Utilization | Approved Limit
 | 1150 | 3645

## Slide 42: Loan Vs Financial Vs Physical Progress
Chart: 
Chart: 
| Loan Utilization | Financial Progress | Physical Progress
 | 0.3155 | 0.4976 | 0.6338