## Sheet1
NEW BUSINESS TAKEOVER CHECKLIST
Company
Checklist Item | Description (If applicable) | Lead Person | Other involvements | By When
HR |  |  |  | Days
Initial meeting with staff |  | MANAGING DIRECTOR |  | 1
Issue staff communication to all staff | Standard template to be amended by MD | MANAGING DIRECTOR | JANET BARNES TO HELP DRAFT | 1
HR Audit | Contact with Peter Lawrence | HR DIRECTOR | MANAGING DIRECTOR | 30
Implement HR Audit recommendations |  | HR DIRECTOR | MANAGING DIRECTOR | 90
Update HR Policies | Peter Lawrence has suite of documents | HR DIRECTOR | HR TEAM | 90
Update Staff Contracts & Employee Handbook & Issue | Peter Lawrence has suite of documents | HR DIRECTOR | HR TEAM | 90
Update Company Org Chart & staff list |  | HR DIRECTOR | JANET BARNES TO HELP DRAFT | 60
MD Initial 1:1 with all staff |  | MANAGING DIRECTOR |  | 30
Consider LLP Implementation & Plan |  | MANAGING DIRECTOR | FINANCE DIRECTOR / HR DIRECTOR | 30
Personal Development Plans issued all staff |  | HR DIRECTOR | HR TEAM | 90
Finance
Initiate Bank Mandate Change (MD/CFO/Finance staff/Ben Seabridge) | Set signing limits (agree with Opulentia) | FINANCE DIRECTOR |  | 7
User access accounting software | Consider moving to Xero / cloud based were applicable | FINANCE DIRECTOR | FINANCE TEAM | 7
Invoice Finance Implementation | Ensure change of bank details communicated to customers (within 7 days), logins, reconcilliations, daily monitoring and cash sweep / daily uploading & draw downs | FINANCE DIRECTOR | FINANCE TEAM / OPULENTIA CEO / FINANCIAL ANALYST | 1
Authorisation process for any expenditure | Set signing limits (agree with Opulentia) | FINANCE DIRECTOR | FINANCE TEAM | 7
Credit Control process updated to best in class | Need to reduce debtor days and have process in place to manage (Call few days before due to remind / issue statement / chaser emails & phone calls day 5, 10, 15, 20 (final overdue) | FINANCE DIRECTOR | FINANCE TEAM | 7
Payroll Process Implemented | Set limits/approval process | FINANCE DIRECTOR | FINANCE TEAM | 7
Update contact details with HMRC |  | FINANCE DIRECTOR | FINANCE TEAM | 30
Completion Accounts | Sometimes deal based on completion accounts - sometimes not - state here is deal dependent or just good practice | FINANCE DIRECTOR |  | 30
HMRC logins |  | FINANCE DIRECTOR | FINANCE TEAM | 7
Ensure debt covenants known by board & monitoring plan |  | FINANCE DIRECTOR | FINANCE TEAM | 7
Stock take |  | FINANCE DIRECTOR | FINANCE TEAM | 30
Update & Check Fixed Asset Register |  | FINANCE DIRECTOR | FINANCE TEAM | 90
Review sales ledger | Credit limits/credit checking / bad debt protection insurance to be considered | FINANCE TEAM | FINANCE TEAM | 30
Review purchase ledger |  | FINANCE TEAM | FINANCE TEAM | 30
Plan tax payments | Ensure VAT / PAYE / Corp Tax in cashflow | FINANCE TEAM | FINANCE TEAM | 14
Update cashflow & monitoring |  | FINANCE TEAM | FINANCE TEAM | 14
Implement Risk Register |  | FINANCE DIRECTOR |  | 30
Daily reporting template installed | Covering cash / debtors / creditors / sales / purchases | FINANCE DIRECTOR | FINANCE TEAM | 14
Stakeholders
Meet/Contact with Key Suppliers |  | MANAGING DIRECTOR |  | 30
Meet/Contact with Key Customers |  | MANAGING DIRECTOR |  | 30
Meet/Contact other Stakeholders (Landlord) |  | MANAGING DIRECTOR |  | 30
Meet/Contact / communication with external funders |  | FINANCE DIRECTOR |  | 14
Meet/Contact Accountant/Auditor |  | FINANCE DIRECTOR |  | 30
Move to new accountant/auditor if applicable |  | FINANCE DIRECTOR |  | 30
Legal
Register any charges at Companies House |  | JANET BARNES | EXTERNAL LAWYER / HEAD OF LEGAL | 14
Register Director changes at Companies House |  | JANET BARNES | EXTERNAL LAWYER / HEAD OF LEGAL | 14
Register change of ownership Companies House (after key stakeholders informed) | do not make changes until key stakeholders communicated with | JANET BARNES | EXTERNAL LAWYER / HEAD OF LEGAL | 14
Initiate Stamp Duty via Lawyers |  | OPULENTIA CEO | EXTERNAL LAWYER | 14
Pay Stamp Duty |  | FINANCE DIRECTOR | OPULENTIA CEO | 28
Update Contact details/notify any corporate body memberships/licenses/permits | list what they are | FINANCE TEAM |  | 30
Business Planning
Refine Business Plan |  | MANAGING DIRECTOR | OPULENTIA CEO / COO / DIRECTOR / CFO | 60
Refine Financial Forecast Model |  | FINANCE DIRECTOR | FINANCIAL ANALYST | 45
Sales Process Documented |  | MANAGING DIRECTOR |  | 90
Marketing Process Documented |  | MANAGING DIRECTOR |  | 90
Financial Process Documented |  | FINANCE DIRECTOR |  | 90
Marketing
Logins for Social Media |  | MANAGING DIRECTOR |  | 30
Logins for Website |  | MANAGING DIRECTOR |  | 30
Website overhaul | We can do basic refresh if needed (not full overhaul) | OPULENTIA COO | MANAGING DIRECTOR | 90
General
Key holder register update |  | FINANCE DIRECTOR | FINANCE TEAM | 30
Computer software and online acces codes |  | FINANCE DIRECTOR |  | 30
Safe combinations | if applicable | FINANCE DIRECTOR |  | 7
Update equipment operating manuals |  | FINANCE DIRECTOR |  | 90
Issue press release about acquisition |  | JANET BARNES | COO | 30
Download data room & ensure access to all parties |  | OPULENTIA CEO |  | 14
Setup Shared Drive for data sharing (HR/Policies/Documents/Financials) |  | JANET BARNES |  | 7
Set up Slack Channel for Board / Senior Leadership team |  | JANET BARNES |  | 7
Review commited orders/sales forward booked |  | MANAGING DIRECTOR | FINANCE DIRECTOR | 30
Update Insurance change of ownership |  | FINANCE DIRECTOR |  | 14
Review insurance with Vista |  | FINANCE DIRECTOR |  | 30
Bill Management Charges & process for futures |  | OPULENTIA CEO | OPULENTIA DIRECTOR / JANET BARNES | 7

## Sheet2
Managing Director | Steve Shore
Executive Assistant (Opulentia) | Janet Barnes
HR Director | Peter Lawrence
Finance Director | Simon Martin
Financial Analyst | Max Kimryakov
Head of Legal | David Marin
External Lawyer | Greg Sher (Gunner Cooke)
Opulentia CEO | Paul Seabridge
Opulentia COO | Mathew Wainwright
Opulentia Director | Goran Pregelj