## 04.9 IO CEP (Stakeholders)
IO Change & Engagement Planning (Stakeholders)
Description: This sheet documents the MOI Intelligence Office Change & Engagement Planning Tracker for Stakeholder Management
| Date: 27.11.24 | [6 empty] | List (Influence ¦ Interest) |  | List (Engagement Matrix) | List (Engagement Pillars) |  | List (Engage Status) | List (Action) | [5 empty] | List (Frequency) | List (Priority) | List (Owner) |  | List (Program Impact) |  |  |  | List (Update)
| Key Assumptions: | [6 empty] | Very High |  | (0) Not Yet Started | (1) Awareness and Alignment |  | Very Strong | Briefing Session (Quick ¦ 45) | [5 empty] | Daily | P1 (in 1W) | Intelligence Office |  | Very High |  |  |  | Planned
| > Stakeholder View for MOI is based on the 2024 MOI Organisation Structure | [6 empty] | High |  | (1) Monitor | (2) Collaboration and Co-Creation |  | Strong | Briefing Session (Long ¦ 90) | [5 empty] | Bi-Weekly | P2 (in 2W) | TBC |  | High |  |  |  | Designed
| > MOI to maintain & refresh stakeholder groups on a quarterly basis | [6 empty] | Medium |  | (2) Keep Informed | (3) Enablement and Capability Building |  | OK | Workshop Session (2 - 3hrs) | [5 empty] | Weekly | P3 (in 3W) |  |  | Medium |  |  |  | Activated
[8 empty] | Low |  | (3) Keep Satisfied | (4) Sustainability and Advocacy |  | Weak | Broadcast (Newsletter) | [5 empty] | Bi-Monthly | P4 (in 4W) |  |  | Low |  |  |  | Realised
[8 empty] | Very Low |  | (4) Manage Closely | TBC |  | Very Weak | Broadcast (Internet) | [5 empty] | Monthly | P5 (in 5W) |  |  | Very Low |  |  |  | Achieved
[8 empty] | TBC |  | TBC |  |  | TBC | Governance Session (Advisory) | [5 empty] | Quarterly | P6 (in 6W) |  |  | TBC |  |  |  | TBC
General Information | [13 empty] | Stakeholder Engagement Plan | [9 empty] | Stakeholder Change (Program Impact) |  |  |  | Calendar (January 2025)
# | Stakeholder Group | Description | Stakeholder Type | Stakeholder Category | Stakeholder Classification (MOI) | Stakeholder Relationship Type (IO) | Stakeholder Relationship Interaction (IO) | Power ¦ Influence | Interest ¦ Involve | Engagement (Target) | Engagement (Pillars) | Engagement (Current) | Engagement (Status | Action (Recommended) | NBA (Suggested) | NBA (Optional) | Next Action Planned | Date Planned | NBA (Channel) | NBA (Frequency) | NBA Priority | Owner (1st) | Owner (2nd) | Governance & Operation | Data & AI Platform | Intelligence Factory | Data & AI Culture | W01 | W02 | W03 | W04
2 | Local Government | Represents emirate-level ministries, regulatory authorities, trade/export agencies, and municipal bodies facilitating localized governance. | Government Institution | Ecosystem (Local) | Ecosystem | Input Provider | Supplies local-level data, trends, and policy impacts required for analytics. | High | High | Keep Satisfied | Awareness and Alignment | (0) Not Yet Started | Weak | Briefing Session (Long ¦ 90) | Workshop Session (2 - 3hrs) | Governance Session (Advisory) | Review & Activate Next Best Action | 2025H1 | Meeting | Quarterly | P6 (in 6W) | Intelligence Office | Intelligence Office | High | High | Medium | Medium | TBC | TBC | TBC | TBC
5 | Investor | Represents foreign direct investors (FDIs) or local individuals/entities interested in contributing to UAE’s economic development. | Individual or Private Sector Entity | Ecosystem (Local & Global) | Ecosystem | Output Recipient | Consumes actionable insights and reports to guide their investment decisions. | High | High | Keep Satisfied | Enablement and Capability Building | (0) Not Yet Started | Weak | Briefing Session (Long ¦ 90) | Workshop Session (2 - 3hrs) | Governance Session (Advisory) | Review & Activate Next Best Action | 2025H1 | Meeting | Bi-Monthly | P6 (in 6W) | Intelligence Office | Intelligence Office | Medium | Medium | High | Medium | TBC | TBC | TBC | TBC
6 | Free Zones and Special Economic Zones | Represents designated areas offering tax incentives, reduced regulation, and tailored services to attract international businesses. | Economic Entity | Ecosystem (Local) | Ecosystem | Hybrid | Provides operational data and utilizes insights to improve investment attraction and retention. | High | High | Keep Satisfied | Collaboration and Co-Creation | (0) Not Yet Started | Weak | Briefing Session (Long ¦ 90) | Workshop Session (2 - 3hrs) | Governance Session (Advisory) | Review & Activate Next Best Action | 2025H1 | Meeting | Quarterly | P6 (in 6W) | Intelligence Office | Intelligence Office | High | High | High | Medium | TBC | TBC | TBC | TBC
7 | Strategic Investor | Represents large-scale investors making anchor investments with significant socio-economic impact within critical sectors. | Individual or Private Sector Entity | Ecosystem (Global) | Ecosystem | Output Recipient | Consumes advanced investment intelligence and market analytics to support decision-making. | High | High | Keep Satisfied | Enablement and Capability Building | (0) Not Yet Started | Weak | Briefing Session (Long ¦ 90) | Workshop Session (2 - 3hrs) | Governance Session (Advisory) | Review & Activate Next Best Action | 2025H1 | Meeting | Bi-Monthly | P6 (in 6W) | Intelligence Office | Intelligence Office | Very High | High | High | Medium | TBC | TBC | TBC | TBC
18 | Local Federal Statistics Office (Federal) | Represents federal-level data collection and dissemination agencies supporting nationwide policy and decision-making processes. | Government Institution | Ecosystem (Local) | Ecosystem | Input Provider | Provides key federal statistics and demographic data for analysis. | High | Medium | Keep Satisfied | Collaboration and Co-Creation | (0) Not Yet Started | Weak | Briefing Session (Long ¦ 90) | Workshop Session (2 - 3hrs) | Governance Session (Advisory) | Review & Activate Next Best Action | 2025H1 | Meeting | Bi-Monthly | P6 (in 6W) | Intelligence Office | Intelligence Office | High | High | High | Medium | TBC | TBC | TBC | TBC
21 | Global Sovereign Wealth Fund | Represents large-scale wealth funds managing foreign assets and investments globally, driving cross-border opportunities. | Financial Entity | Ecosystem (Global) | Ecosystem | Output Recipient | Utilizes intelligence for strategic global investment decisions. | High | Medium | Keep Satisfied | Collaboration and Co-Creation | (0) Not Yet Started | Weak | Briefing Session (Long ¦ 90) | Workshop Session (2 - 3hrs) | Governance Session (Advisory) | Review & Activate Next Best Action | 2025H1 | Meeting | Quarterly | P6 (in 6W) | Intelligence Office | Intelligence Office | High | High | High | Medium | TBC | TBC | TBC | TBC
24 | Minister’s Office | Supports the Minister in daily operations, correspondence, and communication with stakeholders to ensure effective governance. | Office | Ecosystem (Internal) | Team | Output Recipient | Consumes insights to guide the minister’s agenda and strategy. | High | Very High | Manage Closely | Awareness and Alignment | (0) Not Yet Started | Weak | Workshop Session (2 - 3hrs) | Governance Session (Alignment) | Governance Session (Advisory) | Review & Activate Next Best Action | 2025H1 | Meeting | Bi-Monthly | P6 (in 6W) | Intelligence Office | Intelligence Office | High | Medium | High | Medium | TBC | TBC | TBC | TBC
27 | Strategy & Future Department | Drives strategic planning and foresight, ensuring alignment with national priorities and future investment trends. | Department | Ecosystem (Internal) | Team | Output Recipient | Consumes intelligence to align organizational strategies with future trends. | High | Very High | Manage Closely | Sustainability and Advocacy | (0) Not Yet Started | Weak | Workshop Session (2 - 3hrs) | Governance Session (Alignment) | Governance Session (Advisory) | Review & Activate Next Best Action | 2025H1 | Meeting | Bi-Monthly | P6 (in 6W) | Intelligence Office | Intelligence Office | Very High | High | Very High | High | TBC | TBC | TBC | TBC
28 | Minister’s Advisors | Represents expert advisors providing the Minister with insights, recommendations, and analysis to inform decision-making. | Office | Ecosystem (Internal) | Team | Output Recipient | Utilizes insights to provide recommendations and guidance to the minister. | High | Very High | Manage Closely | Awareness and Alignment | (0) Not Yet Started | Weak | Workshop Session (2 - 3hrs) | Governance Session (Alignment) | Governance Session (Advisory) | Review & Activate Next Best Action | 2025H1 | Meeting | Bi-Monthly | P6 (in 6W) | Intelligence Office | Intelligence Office | High | Medium | High | Medium | TBC | TBC | TBC | TBC
29 | Special Investments Projects Department | Focuses on managing and executing high-impact, strategic investment projects to maximize economic growth and development. | Department | Ecosystem (Internal) | Team | Hybrid | Inputs data on project-specific investments and consumes intelligence to optimize project outcomes. | High | High | Keep Satisfied | Collaboration and Co-Creation | (0) Not Yet Started | Weak | Briefing Session (Long ¦ 90) | Workshop Session (2 - 3hrs) | Governance Session (Advisory) | Review & Activate Next Best Action | 2025H1 | Meeting | Monthly | P6 (in 6W) | Intelligence Office | Intelligence Office | High | High | High | Medium | TBC | TBC | TBC | TBC
30 | Undersecretary Office | Provides operational support and coordination for the Undersecretary, ensuring smooth execution of departmental activities. | Office | Ecosystem (Internal) | Team | Output Recipient | Receives reports and insights for administrative decision-making. | High | High | Keep Satisfied | Awareness and Alignment | (0) Not Yet Started | Weak | Briefing Session (Long ¦ 90) | Workshop Session (2 - 3hrs) | Governance Session (Advisory) | Review & Activate Next Best Action | 2025H1 | Meeting | Quarterly | P6 (in 6W) | Intelligence Office | Intelligence Office | High | Medium | High | Medium | TBC | TBC | TBC | TBC
40 | Financial Resources Department | Manages financial planning, budgeting, and resource allocation to support Ministry initiatives and operational stability. | Department | Ecosystem (Internal) | Team | Input Provider | Provides financial performance and budget-related data for decision-making. | High | Medium | Keep Satisfied | Awareness and Alignment | (0) Not Yet Started | Weak | Briefing Session (Long ¦ 90) | Workshop Session (2 - 3hrs) | Governance Session (Advisory) | Review & Activate Next Best Action | 2025H1 | Meeting | Bi-Monthly | P6 (in 6W) | Intelligence Office | Intelligence Office | Medium | Low | Medium | Medium | TBC | TBC | TBC | TBC
43 | Procurement & Contracts Department | Oversees procurement processes, supplier management, and contract administration to ensure value-driven and transparent operations. | Department | Ecosystem (Internal) | Team | Input Provider | Supplies procurement and contract-related data for strategic planning and efficiency. | High | Medium | Keep Satisfied | Awareness and Alignment | (0) Not Yet Started | Weak | Briefing Session (Long ¦ 90) | Workshop Session (2 - 3hrs) | Governance Session (Advisory) | Review & Activate Next Best Action | 2025H1 | Meeting | Bi-Monthly | P6 (in 6W) | Intelligence Office | Intelligence Office | Medium | Low | Medium | Low | TBC | TBC | TBC | TBC
8 | Business Partner | Represents local organizations collaborating with the UAE to promote trade, innovation, and partnership-driven opportunities. | Organization | Ecosystem (Local & Global) | Ecosystem | Hybrid | Provides industry-specific data and receives market intelligence to strengthen partnerships. | Low | Medium | Monitor | Enablement and Capability Building | (0) Not Yet Started | Weak | Briefing Session (Quick ¦ 45) | Broadcast (Internet) | Briefing Session (Quick ¦ 45) | Review & Activate Next Best Action | 2025H1 | Portal | Quarterly | P6 (in 6W) | Intelligence Office | Intelligence Office | Medium | Medium | High | Low | TBC | TBC | TBC | TBC
9 | International Partner | Represents foreign trade bodies, embassies, and multilateral organizations fostering international cooperation and investment. | Organization | Ecosystem (Global) | Ecosystem | Hybrid | Provides cross-border data and receives reports to foster collaboration and cooperation. | Low | Medium | Monitor | Collaboration and Co-Creation | (0) Not Yet Started | Weak | Briefing Session (Quick ¦ 45) | Broadcast (Internet) | Briefing Session (Quick ¦ 45) | Review & Activate Next Best Action | 2025H1 | Portal | Quarterly | P6 (in 6W) | Intelligence Office | Intelligence Office | Medium | Medium | High | Low | TBC | TBC | TBC | TBC
11 | Advisory Partner | Represents consultancy firms and advisory organizations offering strategic guidance, feasibility analysis, and investment due diligence. | Organization | Ecosystem (Local & Global) | Ecosystem | Hybrid | Provides advisory insights and uses intelligence for consultancy and decision-making. | Low | Medium | Monitor | Collaboration and Co-Creation | (0) Not Yet Started | Weak | Briefing Session (Quick ¦ 45) | Broadcast (Internet) | Briefing Session (Quick ¦ 45) | Review & Activate Next Best Action | 2025H1 | Portal | Quarterly | P6 (in 6W) | Intelligence Office | Intelligence Office | Medium | Low | Medium | Low | TBC | TBC | TBC | TBC
12 | Technology Partner | Represents IT firms and solution providers supporting digital transformation initiatives and enabling advanced analytics. | Organization | Ecosystem (Local & Global) | Ecosystem | Hybrid | Inputs technology-related metrics and receives insights for process optimization and digital transformation. | Low | Medium | Monitor | Enablement and Capability Building | (0) Not Yet Started | Weak | Briefing Session (Quick ¦ 45) | Broadcast (Internet) | Briefing Session (Quick ¦ 45) | Review & Activate Next Best Action | 2025H1 | Portal | Quarterly | P6 (in 6W) | Intelligence Office | Intelligence Office | Low | High | Medium | Medium | TBC | TBC | TBC | TBC
13 | Research Partner | Represents academic institutions, think tanks, and R&D centers advancing innovation and contributing to knowledge economies. | Institution | Ecosystem (Local & Global) | Ecosystem | Input Provider | Supplies research outputs, case studies, and analytics support. | Low | Medium | Monitor | Collaboration and Co-Creation | (0) Not Yet Started | Weak | Briefing Session (Quick ¦ 45) | Broadcast (Internet) | Briefing Session (Quick ¦ 45) | Review & Activate Next Best Action | 2025H1 | Portal | Quarterly | P6 (in 6W) | Intelligence Office | Intelligence Office | Low | Medium | Medium | High | TBC | TBC | TBC | TBC
15 | Civil Society Partner | Represents NGOs and social organizations ensuring governance frameworks align with societal, environmental, and economic goals. | Organization | Ecosystem (Local & Global) | Ecosystem | Input Provider | Provides community-related data, challenges, and feedback influencing investment strategies. | Low | Medium | Monitor | Sustainability and Advocacy | (0) Not Yet Started | Weak | Briefing Session (Quick ¦ 45) | Broadcast (Internet) | Briefing Session (Quick ¦ 45) | Review & Activate Next Best Action | 2025H1 | Portal | Quarterly | P6 (in 6W) | Intelligence Office | Intelligence Office | Low | Low | Medium | Medium | TBC | TBC | TBC | TBC
3 | Local Investment Promotion Agency | Partner agencies focusing on facilitating regional investments, promoting local opportunities to domestic and global investors. | Entity | Ecosystem (Local) | Ecosystem | Hybrid | Inputs local economic data and serves as a recipient of insights to drive investment strategies. | Medium | High | Keep Informed | Collaboration and Co-Creation | (0) Not Yet Started | Weak | Briefing Session (Quick ¦ 45) | Broadcast (Newsletter) | Briefing Session (Long ¦ 90) | Review & Activate Next Best Action | 2025H1 | Meeting | Monthly | P6 (in 6W) | Intelligence Office | Intelligence Office | High | Medium | High | Medium | TBC | TBC | TBC | TBC
4 | Global Investment Promotion Agency | Organizations promoting cross-border investments, acting as mediators between foreign investors and local business ecosystems. | Entity | Ecosystem (Global) | Ecosystem | Output Recipient | Receives insights and reports to guide international investment promotion strategies. | Medium | Medium | Monitor | Collaboration and Co-Creation | (0) Not Yet Started | Weak | Briefing Session (Quick ¦ 45) | Broadcast (Internet) | Briefing Session (Quick ¦ 45) | Review & Activate Next Best Action | 2025H1 | Portal | Quarterly | P6 (in 6W) | Intelligence Office | Intelligence Office | Medium | Medium | High | Low | TBC | TBC | TBC | TBC
10 | Business Organization | Represents chambers of commerce, industry-specific associations, and similar entities advocating for enterprise interests. | Organization | Ecosystem (Local & Global) | Ecosystem | Input Provider | Supplies private-sector data, market conditions, and challenges impacting investments. | Medium | Medium | Monitor | Awareness and Alignment | (0) Not Yet Started | Weak | Briefing Session (Quick ¦ 45) | Broadcast (Internet) | Briefing Session (Quick ¦ 45) | Review & Activate Next Best Action | 2025H1 | Portal | Quarterly | P6 (in 6W) | Intelligence Office | Intelligence Office | Medium | Medium | Medium | Low | TBC | TBC | TBC | TBC
14 | Financial Institution | Represents banks, private equity firms, sovereign wealth funds, and financial entities financing economic growth and infrastructure. | Institution | Ecosystem (Local & Global) | Ecosystem | Hybrid | Inputs financial performance and transaction data and consumes intelligence for investment-related services. | Medium | Medium | Monitor | Collaboration and Co-Creation | (0) Not Yet Started | Weak | Briefing Session (Quick ¦ 45) | Broadcast (Internet) | Briefing Session (Quick ¦ 45) | Review & Activate Next Best Action | 2025H1 | Portal | Quarterly | P6 (in 6W) | Intelligence Office | Intelligence Office | Medium | Medium | High | Low | TBC | TBC | TBC | TBC
16 | Media and Communication Partners | Represents organizations delivering targeted communication campaigns and promoting the UAE’s investment landscape internationally. | Organization | Ecosystem (Local & Global) | Ecosystem | Output Recipient | Receives insights and reports to drive communication strategies and public awareness. | Medium | Medium | Monitor | Awareness and Alignment | (0) Not Yet Started | Weak | Briefing Session (Quick ¦ 45) | Broadcast (Internet) | Briefing Session (Quick ¦ 45) | Review & Activate Next Best Action | 2025H1 | Portal | Quarterly | P6 (in 6W) | Intelligence Office | Intelligence Office | Medium | Low | Medium | Medium | TBC | TBC | TBC | TBC
17 | Local Family Office | Represents wealth management offices catering to Emirati families, focusing on private investments and financial structuring. | Private Sector Entity | Ecosystem (Local) | Ecosystem | Output Recipient | Consumes investment intelligence to guide family-level wealth and investment decisions. | Medium | Medium | Monitor | Enablement and Capability Building | (0) Not Yet Started | Weak | Briefing Session (Quick ¦ 45) | Broadcast (Internet) | Briefing Session (Quick ¦ 45) | Review & Activate Next Best Action | 2025H1 | Portal | Monthly | P6 (in 6W) | Intelligence Office | Intelligence Office | Low | Low | High | Low | TBC | TBC | TBC | TBC
19 | Local Statistics Office (Emirate) | Represents emirate-specific statistical bureaus aiding localized strategic planning and analytics efforts. | Government Institution | Ecosystem (Local) | Ecosystem | Input Provider | Supplies emirate-specific statistics to support localized insights and decision-making. | Medium | Medium | Monitor | Collaboration and Co-Creation | (0) Not Yet Started | Weak | Briefing Session (Quick ¦ 45) | Broadcast (Internet) | Briefing Session (Quick ¦ 45) | Review & Activate Next Best Action | 2025H1 | Portal | Monthly | P6 (in 6W) | Intelligence Office | Intelligence Office | High | High | High | Medium | TBC | TBC | TBC | TBC
20 | Local Sovereign Wealth Fund | Represents wealth funds managing and investing emirate-level public financial resources to generate returns and support economic stability. | Financial Entity | Ecosystem (Local) | Ecosystem | Output Recipient | Consumes insights for optimizing portfolio investments and decision-making. | Medium | Medium | Monitor | Collaboration and Co-Creation | (0) Not Yet Started | Weak | Briefing Session (Quick ¦ 45) | Broadcast (Internet) | Briefing Session (Quick ¦ 45) | Review & Activate Next Best Action | 2025H1 | Portal | Monthly | P6 (in 6W) | Intelligence Office | Intelligence Office | High | High | High | Medium | TBC | TBC | TBC | TBC
25 | Internal Audit Office | Represents the office responsible for assessing and ensuring compliance, accountability, and transparency across Ministry operations. | Office | Ecosystem (Internal) | Team | Input Provider | Provides compliance and risk-related data to ensure governance in decision-making. | Medium | Medium | Monitor | Awareness and Alignment | (0) Not Yet Started | Weak | Briefing Session (Quick ¦ 45) | Broadcast (Internet) | Briefing Session (Quick ¦ 45) | Review & Activate Next Best Action | 2025H1 | Portal | Monthly | P6 (in 6W) | Intelligence Office | Intelligence Office | Medium | Medium | Medium | Low | TBC | TBC | TBC | TBC
26 | Government Communication Department | Facilitates internal and external communication, ensuring the Ministry’s messaging aligns with its objectives and public outreach. | Department | Ecosystem (Internal) | Team | Output Recipient | Receives insights to develop communication strategies and messaging for stakeholders. | Medium | High | Keep Informed | Awareness and Alignment | (0) Not Yet Started | Weak | Briefing Session (Quick ¦ 45) | Broadcast (Newsletter) | Briefing Session (Long ¦ 90) | Review & Activate Next Best Action | 2025H1 | Meeting | Bi-Monthly | P6 (in 6W) | Intelligence Office | Intelligence Office | Medium | Low | Medium | Medium | TBC | TBC | TBC | TBC
31 | Legal Affairs Department | Handles legal matters, ensuring compliance with laws, regulations, and drafting policies to support investment-related initiatives. | Department | Ecosystem (Internal) | Team | Input Provider | Provides regulatory and legislative data influencing investment strategies. | Medium | Medium | Monitor | Awareness and Alignment | (0) Not Yet Started | Weak | Briefing Session (Quick ¦ 45) | Broadcast (Internet) | Briefing Session (Quick ¦ 45) | Review & Activate Next Best Action | 2025H1 | Portal | Monthly | P6 (in 6W) | Intelligence Office | Intelligence Office | High | Medium | High | Medium | TBC | TBC | TBC | TBC
35 | Outbound Investment Department | Manages and facilitates UAE’s outbound investments, promoting strategic global partnerships and opportunities. | Department | Ecosystem (Internal) | Team | Hybrid | Inputs outbound investment data and uses intelligence to guide international investment efforts. | Medium | High | Keep Informed | Enablement and Capability Building | (0) Not Yet Started | Weak | Briefing Session (Quick ¦ 45) | Broadcast (Newsletter) | Briefing Session (Long ¦ 90) | Review & Activate Next Best Action | 2025H1 | Meeting | Bi-Monthly | P6 (in 6W) | Intelligence Office | Intelligence Office | Medium | Medium | High | Medium | TBC | TBC | TBC | TBC
36 | Foreign Direct Investment Department | Focuses on attracting and retaining foreign direct investments, ensuring alignment with national economic goals. | Department | Ecosystem (Internal) | Team | Hybrid | Inputs data on FDI performance and consumes insights for attraction strategies. | Medium | High | Keep Informed | Collaboration and Co-Creation | (0) Not Yet Started | Weak | Briefing Session (Quick ¦ 45) | Broadcast (Newsletter) | Briefing Session (Long ¦ 90) | Review & Activate Next Best Action | 2025H1 | Meeting | Bi-Monthly | P6 (in 6W) | Intelligence Office | Intelligence Office | Medium | Medium | High | Medium | TBC | TBC | TBC | TBC
37 | Partnerships and Investment Promotion | Builds and strengthens partnerships with local and global entities to enhance investment promotion efforts. | Department | Ecosystem (Internal) | Team | Hybrid | Inputs partnership data and uses intelligence to enhance investment promotion strategies. | Medium | High | Keep Informed | Collaboration and Co-Creation | (0) Not Yet Started | Weak | Briefing Session (Quick ¦ 45) | Broadcast (Newsletter) | Briefing Session (Long ¦ 90) | Review & Activate Next Best Action | 2025H1 | Meeting | Bi-Monthly | P6 (in 6W) | Intelligence Office | Intelligence Office | Medium | Medium | High | Medium | TBC | TBC | TBC | TBC
38 | Policies and Investment Legislation Department | Develops and enforces policies and legal frameworks to regulate and encourage sustainable investments. | Department | Ecosystem (Internal) | Team | Input Provider | Supplies policy and legislative data critical for strategy alignment. | Medium | High | Keep Informed | Collaboration and Co-Creation | (0) Not Yet Started | Weak | Briefing Session (Quick ¦ 45) | Broadcast (Newsletter) | Briefing Session (Long ¦ 90) | Review & Activate Next Best Action | 2025H1 | Meeting | Bi-Monthly | P6 (in 6W) | Intelligence Office | Intelligence Office | High | Medium | High | Medium | TBC | TBC | TBC | TBC
39 | Human Resources Department | Oversees talent acquisition, training, and workforce planning to ensure organizational efficiency and employee development. | Department | Ecosystem (Internal) | Team | Input Provider | Supplies workforce-related data influencing operational intelligence. | Medium | Medium | Monitor | Enablement and Capability Building | (0) Not Yet Started | Weak | Briefing Session (Quick ¦ 45) | Broadcast (Internet) | Briefing Session (Quick ¦ 45) | Review & Activate Next Best Action | 2025H1 | Portal | Monthly | P6 (in 6W) | Intelligence Office | Intelligence Office | Medium | Low | Medium | Medium | TBC | TBC | TBC | TBC
41 | Digital Transformation Department | Leads digital initiatives, leveraging technology to enhance processes, services, and data management within the Ministry. | Department | Ecosystem (Internal) | Team | Input Provider | Supplies data on technology adoption and performance for alignment with digital strategies. | Medium | Medium | Monitor | Enablement and Capability Building | (0) Not Yet Started | Weak | Briefing Session (Quick ¦ 45) | Broadcast (Internet) | Briefing Session (Quick ¦ 45) | Review & Activate Next Best Action | 2025H1 | Portal | Bi-Monthly | P6 (in 6W) | Intelligence Office | Intelligence Office | Medium | High | High | High | TBC | TBC | TBC | TBC
42 | Administration Affairs Department | Manages the Ministry’s administrative functions, including facilities management, correspondence, and organizational logistics. | Department | Ecosystem (Internal) | Team | Output Recipient | Consumes intelligence for operational optimization and administrative decision-making. | Medium | Medium | Monitor | Awareness and Alignment | (0) Not Yet Started | Weak | Briefing Session (Quick ¦ 45) | Broadcast (Internet) | Briefing Session (Quick ¦ 45) | Review & Activate Next Best Action | 2025H1 | Portal | Quarterly | P6 (in 6W) | Intelligence Office | Intelligence Office | Medium | Low | Medium | Low | TBC | TBC | TBC | TBC
1 | Federal Government | Represents ministries and regulatory authorities operating at a federal level, ensuring nationwide compliance and policy implementation. | Government Institution | Ecosystem (Local) | Ecosystem | Input Provider | Provides regulatory, policy, and operational data essential for analysis and insights. | Very High | Very High | Manage Closely | Awareness and Alignment | (0) Not Yet Started | Weak | Workshop Session (2 - 3hrs) | Governance Session (Alignment) | Governance Session (Advisory) | Review & Activate Next Best Action | 2025H1 | Meeting | Monthly | P6 (in 6W) | Intelligence Office | Intelligence Office | Very High | High | High | High | TBC | TBC | TBC | TBC
22 | Minister | Represents the highest authority within the Ministry, providing strategic direction, oversight, and approval of key initiatives. | Position | Ecosystem (Internal) | Leadership | Output Recipient | Consumes high-level reports and insights for policy and decision-making. | Very High | Very High | Manage Closely | Awareness and Alignment | (0) Not Yet Started | Weak | Workshop Session (2 - 3hrs) | Governance Session (Alignment) | Governance Session (Advisory) | Review & Activate Next Best Action | 2025H1 | Meeting | Monthly | P6 (in 6W) | Intelligence Office | Intelligence Office | Very High | Medium | High | High | TBC | TBC | TBC | TBC
23 | Undersecretary | Represents the principal executive officer responsible for implementing the Ministry’s strategic vision and operational objectives. | Position | Ecosystem (Internal) | Leadership | Output Recipient | Receives intelligence to support governance and administrative decision-making. | Very High | Very High | Manage Closely | Awareness and Alignment | (0) Not Yet Started | Weak | Workshop Session (2 - 3hrs) | Governance Session (Alignment) | Governance Session (Advisory) | Review & Activate Next Best Action | 2025H1 | Meeting | Bi-Monthly | P6 (in 6W) | Intelligence Office | Intelligence Office | Very High | Medium | High | High | TBC | TBC | TBC | TBC
32 | Assistant Undersecretary – Developing and Promoting Investments | Focuses on identifying and facilitating investment opportunities, promoting the UAE as an investment hub. | Position | Ecosystem (Internal) | Leadership | Hybrid | Inputs data on promotional activities and consumes insights to improve investment facilitation. | Very High | High | Manage Closely | Collaboration and Co-Creation | (0) Not Yet Started | Weak | Workshop Session (2 - 3hrs) | Governance Session (Alignment) | Governance Session (Advisory) | Review & Activate Next Best Action | 2025H1 | Meeting | Bi-Monthly | P6 (in 6W) | Intelligence Office | Intelligence Office | High | Medium | High | Medium | TBC | TBC | TBC | TBC
33 | Assistant Undersecretary – Policies and Investment Legislation | Responsible for formulating and updating policies, regulations, and legislation to support a conducive investment environment. | Position | Ecosystem (Internal) | Leadership | Input Provider | Supplies data on policy frameworks and legislative impacts. | Very High | High | Manage Closely | Collaboration and Co-Creation | (0) Not Yet Started | Weak | Workshop Session (2 - 3hrs) | Governance Session (Alignment) | Governance Session (Advisory) | Review & Activate Next Best Action | 2025H1 | Meeting | Bi-Monthly | P6 (in 6W) | Intelligence Office | Intelligence Office | High | Medium | High | Medium | TBC | TBC | TBC | TBC
34 | Assistant Undersecretary – Support Services | Oversees administrative, logistical, and financial services to ensure seamless Ministry operations. | Position | Ecosystem (Internal) | Leadership | Output Recipient | Utilizes intelligence for managing support services effectively. | Very High | High | Manage Closely | Awareness and Alignment | (0) Not Yet Started | Weak | Workshop Session (2 - 3hrs) | Governance Session (Alignment) | Governance Session (Advisory) | Review & Activate Next Best Action | 2025H1 | Meeting | Bi-Monthly | P6 (in 6W) | Intelligence Office | Intelligence Office | High | Medium | Medium | Medium | TBC | TBC | TBC | TBC
Note on AC12: Calendar Established for one Month of 2025 as illustration for planning only.
Return to Home