## Doc Control
YOUR LOGO
Document Control
Info | Description
Titles | Risk Assessment and Treatment Table
Ref number: | ID-01-0001 |  |  | Version: | 1.1
Classification: | Public | Internal use |  | Confidentiality |  | Confidential and restricted
Data Owner: | Ertan | Iliyaz |  | Date: |  | 03.04.2025
Document Author
Version number | Date | Author | Comment
1 | 2025-03-04 | CISO | Risk Identifcation, Heatmap and Matrix has been created
1.1 | 2025-05-04 | CISO | Risk Workflow, Info and CIA informations has been added
Document review
Version number | Date | Position | Comment
1.1 | 2025-08-04 | Risk | Confirmed
Document Aprove
Version number | Date | Position | Comment
1.1 | 2025-08-04 | CEO | Aproved

## Risk Identification
NAME | Company Name | Version 1.0 |  |  |  |  | OBJECTIVE | Risk Assesment and Risk Treatment Matrix
PRE-MITIGATION | [13 empty] | POST-MITIGATION
Risk no | Column1 | Risk ID | Risk Owner | Date Identified | Status | Risk Description | Impact Desciption | Impact | Probaility | Risk Score | Confidentiality (L, M, H) | Integrity (L, M, H) | Availability (L, M, H) | Risk Treatment Required? (Y/N) | Risk Treatment (M, A, Av, T) | RISK LEVEL | Comment
1 |  | Risk01 | Ertan Iliyaz | 2025-03-04 | Open | Technician will not be avaiable during May | Product build will be delayed by 1 month | 5 | 4 | 20 | L | L | L | Y | T | L
2 |  | Risk02 | Ertan Iliyaz | 2025-03-05 | Open | Not available prototype | customer validation prototpes will be delayed | 3 | 4 | 12 | L | L | L | Y | T | L
3 |  | Risk03 | Ertan Iliyaz | 2025-03-06 | Open | X Updateds not implemented | vulnerable from outsite attack | 2 | 2 | 4 | L | L | L | Y | T | L
4 |  | Risk04 | Ertan Iliyaz | 2025-03-07 | Open | Y Updateds not implemented | vulnerable from outsite attack | 5 | 3 | 15 | L | L | L | Y | T | L
5 |  | Risk05 | Ertan Iliyaz | 2025-03-08 | Open | Z Updateds not implemented | vulnerable from outsite attack | 4 | 2 | 8 | L | L | L | Y | T | L
6 |  | Risk06 | Ertan Iliyaz | 2025-03-09 | Open | Not available prototype | Customer validation prototpes will be delayed | 1 | 5 | 5 | L | L | L | Y | T | L

## CIA
Suggested keys
Confidentiality |  | Risk Treatment Recommendations
Confidentiality Level | Confidentiality Definition | Risk Treatment | Risk Treatment Definition | Key
High | Information which is very sensitive or private, of highest value to the organization and intended to use by named individuals only. The unauthorized disclosure of such information can cause severe harm (e.g. Legal or financial liability, adverse competitive impact, loss of brand name). E.g. Merger and Acquisition related information, Marketing strategy, etc. | Risk reduction/mitigation | The level of risk should be reduced through the selection of controls so that the residual risk can be re-assessed as being acceptable. | M
Medium | Information belonging to the organization and not for disclosure to public or external parties. The unauthorized disclosure of information here can cause a limited harm to the organization. e.g. Organization Charts, Internal Telephone Directory. | Risk acceptance | If the level of risk meets the risk acceptance criteria, there is no need for implementing additional controls and the risk can be retained. | A
Low | Non-sensitive information available for public disclosure. The impact of unauthorized disclosure of such information shall not harm the organization in any way. E.g. Press releases, organization newsletters, information published on organization’s public website, etc. | Risk avoidance | The activity or condition that gives rise to the particular risk should be avoided by withdrawing from an activity or changing the conditions under which the activity is operated. | Av
|  | Risk transfer | Transfer the risk to another entity (such as by contract or insurance). | T
Integrity
Integrity Requirement | Integrity Definition
High | Integrity degradation is unacceptable.
Medium | There is significant impact on the organization if the accuracy and completeness of data is degraded.
Low | There is minimal impact on the organization if the accuracy and completeness of data is degraded.
Availability
Availability Requirement | Availability Definition
High | The asset / information is required on 24x7 basis
Medium | There is significant impact on the organization if the asset / information is not available for up to 24 hours.
Low | There is minimal impact on the organization if the asset / information is not available for up to 48 hours.

## KEY - Risk Assessment Matrix
RISK MATRIX
Probability | 5 | 5 | 10 | 15 | 20 | 25
| 4 | 4 | 8 | 12 | 16 | 20 | ColorCode | Score | Result | Result
| 3 | 3 | 6 | 9 | 12 | 15 | Extrem | >20 | 20 to 25 | Extrem
| 2 | 2 | 4 | 6 | 8 | 10 | High | 6 -- 16 | 12 to 16 | High
| 1 | 1 | 2 | 3 | 4 | 5 | Medium | 5 -- 10 | 6 to 10 | Medium
|  | 1 | 2 | 3 | 4 | 5 | Low | 1 -- 4 | 1 to 5 | Low
Impact

## Risk Workflow
RISK MANAGEMENT WORKFLOW
Risk Management Approach | Identification of Assets | Assesment of Impact |  | Risk Mitigation
Risk Evaluation Criteria | Identification of Threats | Assesment of Likehood |  | Risk Avoidance
Risk Acceptance Criteria | Identification of existing Controls | Assesment of Risk Level |  | Risk Transfer
Scope and Boundaries | Identification of Vulnerabilities |  |  | Risk Acceptance
Organization | Identification of Impact
Do you Accept the Risk
Establish Context | Risk idntiifcation | Risk Analysis | Risk Evluation | Risk Treatment |  | Risk Monitoring and Review
NO
YES