# Co‑Creation Workshop Plan — Evolving Work with AI

Kenny’s Change Lab (KCL) • kennyschangelab.com

## Audience & Objectives

Audience: cross‑functional team (Managers, ICs, Risk/Legal, Data/IT, HR/L&D). Objective: co‑design a ‘team + agent’ workflow, agree guardrails, define success metrics (APV), and plan a 30‑day experiment.

## Agenda (120 minutes)

• 00:00–00:10 — Welcome, goals, psychological safety norms

• 00:10–00:25 — Context: why this workflow, current pain/risks, desired outcomes

• 00:25–00:50 — Map the work: intake → triage → propose → decide → execute → learn (Swimlane: Agent | Human | Controls)

• 00:50–01:05 — Guardrails: pre‑approved use cases, PII rules, logging, human‑in‑the‑loop, incident path (align to NIST & ISO practices)

• 01:05–01:25 — Metrics: define APV (Adoption, Proficiency, Value) and risk indicators; draft the one‑page scorecard

• 01:25–01:40 — 30‑day experiment: who/what/when; prompt packs, job aids, office hours

• 01:40–02:00 — Commitments, owners, decision dates; close and feedback pulse

## Materials & Templates

• Swimlane canvas (Agent / Human / Controls)
• Guardrail checklist
• APV scorecard sheet
• Risk heatmap (Impact × Likelihood)
• Experiment charter (Hypothesis, Metrics, Owners, Start/End)

## Roles & RACI (Lite)

Sponsor (A/R), Product/Process Owner (R), Change Lead (R), Data/IT (C/R), Risk/Legal (C), HR/L&D (C), Team Managers (R), Champions (R), PMO (C).

## Success Criteria

• One workflow mapped and instrumented
• Guardrails agreed and documented
• APV scorecard populated (targets + leading indicators)
• 30‑day experiment with clear owners, artifacts, and check‑ins
• Review booked at Day 30 to decide scale/iterate/stop