# Sponsor Enablement Kit — AI Adoption & Future of Work

Kenny’s Change Lab (KCL) • kennyschangelab.com

## Purpose

Enable executive sponsors to lead visible, repeatable behaviors that land AI adoption safely and measurably. This kit maps actions to the NIST AI RMF (Govern, Map, Measure, Manage) and ISO/IEC 42001 practices, with an EU AI Act–aware planning lens.

## Sponsor Standard Work (Weekly)

• Publish a simple narrative: knowns, unknowns, next decision dates.

• Hold a 15‑minute APV review (Adoption • Proficiency • Value) — one action per tier.

• Show up where the work lives: floor time, skip‑levels, open office hours.

• Remove one blocker a week (policy, access, tooling, staffing) and close the loop in writing.

• Model the habits: use the same prompt packs, job aids, and governance paths you expect teams to use.

## Decision & Escalation Path

Red‑flag path for risks to safety, compliance, brand, SLAs, or people impact:
1) Team logs issue with owner and due date
2) Stream lead + Change Lead triage within 24 hours
3) Escalate to Sponsor/PMO if unresolved; document resolution on the source‑of‑truth page

## Mapping to NIST AI RMF & ISO/IEC 42001

• NIST: Govern: Tone at the top, risk appetite, roles, accountability, continuous improvement cadence.

• NIST: Map: Inventory AI uses, context & risk, data considerations, stakeholders & impacts.

• NIST: Measure: Define metrics and tests (bias, robustness, security), monitor with APV + risk indicators.

• NIST: Manage: Controls, incident handling, change mgmt, vendor oversight, periodic review.

• ISO 42001: AIMS: Policies → processes → records. Internal audits, management review, supplier management, competence & training.

## EU AI Act — Planning Lens (Indicative)

Plan readiness across 2025–2027 with quarterly checkpoints. Focus on inventory & classification, baseline controls (logging, data protection, human oversight), and supplier clauses. Treat dates as planning anchors; confirm regulatory timing with Legal.

## Sponsor Checklist (Use Weekly)

□ I communicated decisions and dates clearly this week.

□ I removed at least one blocker and acknowledged the team publicly.

□ Our APV scorecard is updated and drove one action per tier.

□ I verified a guardrail in practice (logging, PII handling, human‑in‑the‑loop).

□ I modeled the change (demoed, asked questions, recognized learning).

## Artifacts Included / Referenced

• APV scorecard template (Google Sheets)
• Manager huddle script (10 minutes)
• Risk heatmap fields
• Prompt pack pattern (1 task • 3 examples • 1 pitfall • 1 quality check)