## Tracker
Company:
Client:
Project:
| Date: | 2025-09-04
Package Number | Description | Contract Type | Area | Status | Engineer | Contract Admin | Design Package | Design Stage for ITT | Design Due Date | Package Review |  | Days | ITT complete & Issue to Market |  | Days | Return of Tenders |  | Days | Tender Analysis / Contract Negotiation |  | Days | Approval |  | Days | Award Date |  | Days | Required on Site (ROS)
[10 empty] | Target Date | Actual Date |  | Target Date | Actual Date |  | Target Date | Actual Date |  | Target Date | Actual Date |  | Target Date | Actual Date |  | Target Date | Actual Date |  | Target Date | Actual Date
CMC-SUP-001 | HV Switchboards | Supply Agreement | North Civil | Design Pending | HG | CM | DES-WBN-001 | 50% | 2025-09-15 | 2025-09-22 |  | 10 | 2025-10-02 |  | 21 | 2025-10-23 |  | 21 | 2025-11-13 |  | 2 | 2025-11-15 |  | 2 | 2025-11-17 |  | 15 | 2025-12-02
CMC-CSA-002 | Ecologist | Consultacy | Tunnel | Out to Tender | YU | JB | DES-WBN-002 | 70% | 2026-01-12 | 2026-01-19 |  | 10 | 2026-01-29 |  | 21 | 2026-02-19 |  | 21 | 2026-03-12 |  | 2 | 2026-03-14 |  | 2 | 2026-03-16 |  | 15 | 2026-03-31
CMC-SUB-003 | FRP Tanks | Subcontract | BLD 1 | Awarded | CC | EA | DES-WBN-003 | IFC | 2026-02-14 | 2026-02-21 |  | 10 | 2026-03-03 |  | 21 | 2026-03-24 |  | 21 | 2026-04-14 |  | 2 | 2026-04-16 |  | 2 | 2026-04-18 |  | 15 | 2026-05-03
Formulas:
Package Review = [Design Due Date]+7
ITT complete & Issue to Market = [Days]+[Package Review]
Return of Tenders = [Days]+[ITT complete & Issue to Market]
Tender Analysis / Contract Negotiation = [Days]+[Return of Tenders]
Approval = [Days]+[Tender Analysis / Contract Negotiation]
Award Date = [Days]+[Approval]
Required on Site (ROS) = [Days]+[Award Date]
Note on E5: Callum Cryans: Drop down list
Note on I5: Callum Cryans: Drop down list

## Drop Down
Design Stage | Status
Preliminary Design | Design Pending
50% | ITT to be Prepared
70% | Out to Tender
90% | Negotiation
100% | Awarded
IFC | Cancelled