# Asset Management Live Training Course

# Program Management Timeline

| Program: Asset Management Date(s): March 2019 |  |  |  |
| --- | --- | --- | --- |
| Project Code AM-19 Fiscal Year: 2018-2019 |  |  |  |
| Venue/Locations: TBD |  |  |  |
| Target Audience: Water and wastewater utility operators, managers, and board members from various states in the US and US Territories |  |  |  |
| ## Pre-Course Tasks | ## Assigned To | Due Date | ##### Completed |
| Initial program planning meeting - Discuss: Program dates, location, target audience, format etc. | All | 12/7/18 | 12/7/18 |
| ### Begin Program Review - Review current curriculum, analyze training gaps, propose recommendations and next steps. | Intern | 12/29/18 | 1/12/19 |
| ### Begin Program Development ### Develop evaluation plan and revise learning objectives for at least two components of current Asset Training curriculum. | Intern | 1/2/19 |  |
| Design Initial Content - Develop learning objectives, training materials and evaluation tool for Asset Management curriculum | Intern | 3/1/19 |  |
| Review developed curriculum and evaluation tool with client | Intern | 3/2/19 |  |
| Revise curriculum and evaluation tool based on client feedback | Intern | 3/9/19 |  |
| Provide final intervention product to cient Discuss program topics & format, speakers, materials) | Intern | 3/17/19 |  |
| ### Project Meetings: Jan 5, Feb 2, Feb 16, Mar. 2, Mar. 9. Meetings online via Zoom or Blackboard Collaborate | Intern and Clients |  |  |
| First Project Planning Meeting | Intern and Clients | 1/5/19 | 1/12/19 |
| Project Planning Meeting – Zoom 30 minutes | Intern and Clients | 2/2/19 |  |
| Project Planning Meeting – Zoom 30 minutes | Intern and Clients | 3/2/19 |  |
| Project Planning Meeting – Zoom 30 minutes | Intern and Clients | 3/9/19 |  |
| Final In-Person Meeting – In person 1 – 2 hours | Intern and Clients | 3/15/19 |  |