| Timeline | Board of Directors | Executive Committee | Search Committee | CEO |
| --- | --- | --- | --- | --- |
| 2024 - Oct |  |  |  | 24 – 31 1:1 meetings with EC members |
|  |  |  |  | 29 Call with Search Firms to request search proposal |
| 2024 - Nov |  | 5 EC planning call |  |  |
|  | 15 Executive Session BOT meeting via zoom for notification in advance of full membership communication | 19 Follow up with potential search firm(s). |  | 11 (week of) 1:1 meetings with staff 15 Personal calls to VIPs, Past Presidents |
|  | 21 Board Meeting, BOD approve: Search Firm Succession Plan Communication Strategy Search Committee Charter Search Committee Roster |  |  |  |
|  | 25 Publish Job Posting | 25 Invitations to Search Committee |  |  |
| 2024 - Dec | Encourage applications | Encourage applications | Encourage applications | Encourage applications |
|  | 31 Deadline to Apply |  | Meetings with Search Firm to review process / dates | 6 180-day notice per contract |
| 2025 - Jan / Feb |  |  | Process led by search firm; including round 1 interviews | Assist with documents for candidate packets |
| March 10 | IPA Board of Trustees Meeting – finalist interviews |  |  |  |
| March – May |  | Extend / Negotiate contract offer |  |  |
| June (early) | New CEO start Exact date (TBD) |  |  | Final day – Flexible (Annual Meeting June 5-6) |