## Gantt Chart (Project Schedule)
Project Title: CADANGAN MEMBINA SEBUAH BANGLO 2 TINGKAT BERSERTA SEBUAH KOLAM RENANG DI ATAS LOT 1234 (PT23456), NO.14, JALAN CUMARASAMI, TAMAN KAYA OFF JALAN IPOH, 51100 KUALA LUMPUR, WILAYAH PERSEKUTUAN KUALA LUMPUR, MALAYSIA.
Shockwave Builder Sdn Bhd
No.14, Jalan Cumarasami, Taman Kaya off Jalan Ipoh, 51100 Kuala Lumpur, Malaysia. Mobile: +6015-987 6543 Office: +603-9999 6543 Email: info@shockwave.my Website: www.shockwave.my |  |  | Project Manager: |  | John Smith
|  |  | Prepare By: |  | Andrew
|  |  | Project Start: |  | 2025-07-01
|  |  | Today Date: |  | 2025-07-09
GANTT CHART by ShockwaveBuilders.com |  |  | Display Week: |  | 1
https://www.ShockwaveBuilders.com/free-construction-gantt-chart-template | [7 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14 | [6 empty] | 2025-07-21 | [6 empty] | 2025-07-28 | [6 empty] | 2025-08-04 | [6 empty] | 2025-08-11 | [6 empty] | 2025-08-18 | [6 empty] | 2025-08-25 | [6 empty] | 2025-09-01 | [6 empty] | 2025-09-08 | [6 empty] | 2025-09-15 | [6 empty] | 2025-09-22 | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12 | [6 empty] | 2026-01-19 | [6 empty] | 2026-01-26 | [6 empty] | 2026-02-02 | [6 empty] | 2026-02-09 | [6 empty] | 2026-02-16 | [6 empty] | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30 | [6 empty] | 2026-04-06 | [6 empty] | 2026-04-13 | [6 empty] | 2026-04-20 | [6 empty] | 2026-04-27 | [6 empty] | 2026-05-04 | [6 empty] | 2026-05-11 | [6 empty] | 2026-05-18 | [6 empty] | 2026-05-25 | [6 empty] | 2026-06-01 | [6 empty] | 2026-06-08 | [6 empty] | 2026-06-15 | [6 empty] | 2026-06-22 | [6 empty] | 2026-06-29
ITEM | TASK | ASSIGNED TO | PROGRESS | START | END | Work Days | time axis 2025-06-30 to 2026-07-05
 | time axis 2025-06-30 to 2026-07-05
PHASE 1: Pre-Construction (Design & Planning)
1 | Site visit & measurement | Chew | 100% | 2025-07-01 | 2025-07-02 | 2 | 2
2 | Client briefing & concept proposal | Faizal | 90% | 2025-07-03 | 2025-07-17 | 15
3 | Architectural, ID, M&E drawings | Azlan, Maslinda, Jack | 80% | 2025-07-06 | 2025-07-20 | 15
3.1 | Architectural drawings | Azlan | 70% | 2025-07-10 | 2025-07-19 | 10
3.2 | M&E drawings | Jack | 60% | 2025-07-14 | 2025-07-22 | 9
3.3 | ID drawings | Maslinda | 50% | 2025-07-18 | 2025-08-01 | 15
4 | Submission to Authorities (PBT, BOMBA, TNB, IWK) | Azlan, Maslinda, Jack | 40% | 2025-07-23 | 2025-08-06 | 15
4.1 | DBKL Authorities Submission | Azlan | 30% | 2025-07-28 | 2025-08-06 | 10
4.2 | TNB Authorities Submission | Azlan | 20% | 2025-08-02 | 2025-08-10 | 9
4.3 | IWK Authorities Submission | Jack | 10% | 2025-08-07 | 2025-08-21 | 15
5 | Cost estimation & contract signing | John Chew | 8% | 2025-08-12 | 2025-08-26 | 15
6 | Project planning & scheduling | Azlan | 5% | 2025-08-17 | 2025-08-31 | 15
7 | BQ & Tender Documents | Kumar | 0% | 2025-08-22 | 2025-09-05 | 15
8 |  |  | 0% |  | 0 | 1
PHASE 2: Construction / Structural (With Floor-Based Structure)
1 | Site Preparation | SWB - John | 100% | 2025-07-16 | 2025-07-30 | 15 | 15
1.1 | Site clearing & hoarding | SWB - Andrew | 90% | 2025-07-21 | 2025-08-11 | 22 | 22
1.2 | Soil investigation | SWB - Azman | 80% | 2025-07-28 | 2025-08-29 | 33 | 33
1.3 | Earthworks (cut & fill) | SWB - Azman | 70% | 2025-08-07 | 2025-08-26 | 20
1.4 | Temporary power/water/site office setup | SWB - John | 60% | 2025-08-17 | 2025-08-27 | 11
2 | Substructure Works | SWB - Andrew | 50% | 2025-08-27 | 2025-09-10 | 15
2.1 | Piling (if required) | SWB - John | 50% | 2025-09-06 | 2025-09-23 | 18 | 18
2.2 | Pile cap | SWB - Azman | 50% | 2025-09-16 | 2025-09-23 | 8 | 10
2.3 | Ground beam | SWB - Andrew | 50% | 2025-09-26 | 2025-10-02 | 7 | 7
2.4 | Ground floor slab casting | SWB - John | 50% | 2025-10-06 | 2025-10-16 | 11 | 11
3 | Superstructure Works Ground Floor | SWB - Andrew | 40% | 2025-10-16 | 2025-10-30 | 15
4 | Superstructure Works First Floor | SWB - Andrew | 30% | 2025-10-26 | 2025-11-16 | 22
5 | Superstructure Works Second Floor | SWB - Andrew | 20% | 2025-11-05 | 2025-12-04 | 30
6 | Superstructure Works Roof Slab (RC Flat Roof) | SWB - Andrew | 20% | 2025-11-15 | 2025-11-29 | 15
7 | Roof waterproofing | SWB - John | 15% | 2025-11-25 | 2025-12-14 | 20
8 | Wall & Ceiling Works | SWB - Azman | 12% | 2025-12-05 | 2025-12-19 | 15
8.1 | Brick wall | SWB - John | 10% | 2025-12-15 | 2026-01-13 | 30
8.2 | Wall & ceiling skim coating | SWB - Azman | 10% | 2025-12-25 | 2026-01-08 | 15
9 | M&E First Fix | SWB - Azman | 50% | 2025-12-09 | 2025-12-14 | 6
9.1 | Electrical conduit & trunking | SWB - Andrew | 40% | 2025-12-09 | 2025-12-30 | 22
9.2 | Cold & hot water piping | SWB - Rajah | 30% | 2025-12-15 | 2025-12-29 | 15
9.3 | Drainage and waste piping | SWB - John | 20% | 2025-12-25 | 2026-01-13 | 20
9.4 | Air-cond copper piping | SWB - Andrew | 10% | 2026-01-04 | 2026-01-14 | 11
10 |  |  | 0% |  |  | 1
PHASE 3: Architectural / Interior Finishing
1 | Flooring Works | SWB - John | 100% | 2025-07-31 | 2025-08-11 | 12 | 12
1.1 | Screeding | SWB - John | 90% | 2025-08-07 | 2025-08-26 | 20
1.2 | Tiling | SWB - John | 80% | 2025-08-14 | 2025-09-17 | 35
1.3 | Timber flooring installation (for bedrooms/living) | SWB - Andrew | 70% | 2025-08-21 | 2025-09-14 | 25
2 | Ceiling Works | SWB - Azman | 60% | 2025-09-10 | 2025-09-16 | 7 | 7
2.1 | Plaster Ceiling | SWB - Azman | 50% | 2025-09-17 | 2025-10-04 | 18 | 18
2.2 | L-box & gypsum ceiling finishing | SWB - John | 40% | 2025-09-24 | 2025-10-05 | 12
3 | Painting Works | SWB - Azman | 30% | 2025-10-01 | 2025-11-03 | 34
3.1 | Primer coats (internal & external) | SWB - John | 20% | 2025-10-08 | 2025-10-26 | 19
3.2 | Paint coats (internal & external) | SWB - Azman | 10% | 2025-10-20 | 2025-11-08 | 20
3 | M&E Final Fix | SWB - Andrew | 30% | 2025-10-27 | 2025-11-16 | 21
3.1 | Lighting & power points | SWB - Andrew | 10% | 2025-11-03 | 2025-11-07 | 5
3.2 | Switches & sockets | SWB - Andrew | 10% | 2025-11-08 | 2025-11-13 | 6
3.3 | Sanitary ware | SWB - Azman | 10% | 2025-11-13 | 2025-11-19 | 7
3.4 | Air-cond, water heater, pump installation | SWB - John | 10% | 2025-11-18 | 2025-11-25 | 8 | 8
3.5 | Smart home system | SWB - John | 10% | 2025-11-25 | 2025-11-29 | 5 | 5
4 |  |  | 0% |  |  | 1
PHASE 4: External Works
1 | Drainage & Sewerage | SWB - John | 25% | 2025-07-21 | 2025-08-13 | 23 | 24
1.1 | Underground drainage pipes | SWB - John | 50% | 2025-08-01 | 2025-08-23 | 22 | 23
1.2 | Manholes (drainage) | SWB - John | 50% | 2025-08-12 | 2025-09-02 | 21 | 22
1.3 | Sewerage pipes (toilet waste) | SWB - Andrew | 50% | 2025-08-23 | 2025-09-12 | 20 | 21
1.4 | Sewer manholes & inspection chambers | SWB - Andrew | 50% | 2025-09-03 | 2025-09-21 | 18 | 19
1.5 | Connection to IWK | SWB - John | 50% | 2025-09-14 | 2025-09-19 | 5 | 6
2 | OSD Tank (On-Site Detention) | SWB - Azman | 50% | 2025-09-03 | 2025-10-11 | 38 | 39
2.1 | Excavation | SWB - Azman | 50% | 2025-09-14 | 2025-09-29 | 15 | 16
2.2 | RC tank base & walls | SWB - Azman | 50% | 2025-09-25 | 2025-10-08 | 13 | 14
2.3 | Cover slab & inspection opening | SWB - Azman | 50% | 2025-10-06 | 2025-10-11 | 5 | 6
2.4 | Connection to overflow/outlet drainage | SWB - Azman | 50% | 2025-10-11 | 2025-10-16 | 5 | 6
3 | Car Porch, Driveway & Landscape Base | SWB - Andrew | 50% | 2025-10-06 | 2025-10-12 | 6 | 7
3.1 | Ground levelling & slab casting | SWB - Andrew | 50% | 2025-10-13 | 2025-10-22 | 9 | 10
3.2 | Tiling or broom finish | SWB - Andrew | 50% | 2025-10-20 | 2025-10-31 | 11 | 12
3.3 | Perimeter drain | SWB - Andrew | 50% | 2025-10-27 | 2025-11-05 | 9 | 10
3.4 | Fencing & auto gate | SWB - Andrew | 50% | 2025-11-03 | 2025-11-05 | 2 | 3
3.5 | Turfing & planting | SWB - Andrew | 50% | 2025-11-03 | 2025-11-18 | 15 | 16
4 |  |  | 0% |  | 0 | 0
PHASE 5: Testing, Approvals & Handover
1 | Testing & Commissioning | SWB - John | 90% | 2025-07-31 | 2025-08-05 | 5 | 6
1.1 | Electrical, water pressure, air-cond, etc. | SWB - John | 80% | 2025-08-05 | 2025-08-10 | 5 | 6
2 | Snagging & Rectification | Azlan, Maslinda, Jack, John | 70% | 2025-08-10 | 2025-08-30 | 20 | 21
2.1 | Walkthrough, touch-up, fix defects | Azlan, Maslinda, Jack, John | 60% | 2025-08-15 | 2025-09-04 | 20 | 21
3 | CCC & Final Authority Submissions | Azlan, Jack | 50% | 2025-08-20 | 2025-09-09 | 20 | 21
3.1 | Architect & Engineer inspections | Azlan, Jack | 40% | 2025-09-09 | 2025-09-14 | 5 | 6
3.2 | Submission to PBT, BOMBA, TNB, IWK | Azlan, Jack | 40% | 2025-09-14 | 2025-10-04 | 20 | 21
4 | Final Handover | Azlan, Maslinda, Jack, John | 30% | 2025-10-04 | 2025-10-05 | 1 | 2
4.1 | Key handover | Azlan, Maslinda, Jack, John | 20% | 2025-10-04 | 2025-10-05 | 1 | 2
4.2 | Documentation (warranty, drawings, certs) | Azlan, Maslinda, Jack, John | 10% | 2025-10-04 | 2025-10-05 | 1 | 2
5 |  |  | 0% |  | 0 | 0
note: Insert new rows ABOVE this one (https://www.ShockwaveBuilders.com/free-construction-gantt-chart-template) | bar: 2025-06-30 to 2025-09-17
Instruction:
1. Change the Company LOGO & Company DETAIL.
2. Fill in the CELL with BORDERS (Project Title, Manager, Start Date, Display Week)
3. The PROJECT START will determine the week the project start and will always show the full week starting on Monday.
4. The TODAY DATE will be display in the chart with 2 RED LINES.
5. The DISPLAY WEEK if you change the week to "14" it will display the chart starting for Week 14. (week 1 to week 13 will be hidden/for easy printing)
6. We have use the INCREASE INDENT to differentiate the sub-task
7. Once you fill in the START & WORK DAYS the END date will automatically change.
8. When you change the % of PROGRESS the progress bar on the right will display the work completion.
9. To add ADDITIONAL ROW you just need to insert row and the formular will retain. (if the formular do not appear you can copy & paste the previous row)
10. The Gantt Chart / Project Schedule are pre-prepare for a 1 years project you can delete the extra column or change the DISPLAY WEEK as the project progresses.

## Importanat Notes
Project Title: CADANGAN MEMBINA SEBUAH BANGLO 2 TINGKAT BERSERTA SEBUAH KOLAM RENANG DI ATAS LOT 1234 (PT23456), NO.14, JALAN CUMARASAMI, TAMAN KAYA OFF JALAN IPOH, 51100 KUALA LUMPUR, WILAYAH PERSEKUTUAN KUALA LUMPUR, MALAYSIA.
Shockwave Builder Sdn Bhd
No.14, Jalan Cumarasami, Taman Kaya off Jalan Ipoh, 51100 Kuala Lumpur, Malaysia. Mobile: +6012-987 6543 Office: +603-9087 6543 Email: info@shockwave.my Website: www.shockwave.my |  |  | Project Manager: |  | John Smith
|  |  | Prepare By: |  | Andrew
|  |  | Project Start: |  | 2025-06-29
|  |  | Today Date: |  | 2025-07-09
GANTT CHART by ShockwaveBuilders.com |  |  | Display Week: |  | 1
https://www.ShockwaveBuilders.com/ExcelTemplates/simple-gantt-chart | [7 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14 | [6 empty] | 2025-07-21 | [6 empty] | 2025-07-28 | [6 empty] | 2025-08-04 | [6 empty] | 2025-08-11 | [6 empty] | 2025-08-18 | [6 empty] | 2025-08-25 | [6 empty] | 2025-09-01 | [6 empty] | 2025-09-08 | [6 empty] | 2025-09-15 | [6 empty] | 2025-09-22 | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03
ITEM | TASK | ASSIGNED TO | PROGRESS | START | END | Work Days | time axis 2025-06-30 to 2025-11-09
 | time axis 2025-06-30 to 2025-11-09
PHASE 1: Pre-Construction (Design & Planning)
1 | Site visit & measurement | Chew | 100% | 2025-06-29 | 2025-06-30 | 2 | 2
2 | Client briefing & concept proposal | Faizal | 90% | 2025-07-01 | 2025-07-15 | 15
3 | Architectural, ID, M&E drawings | Azlan, Maslinda, Jack | 80% | 2025-07-04 | 2025-07-18 | 15
3.1 | Architectural drawings | Azlan | 70% | 2025-07-08 | 2025-07-17 | 10
3.2 | M&E drawings | Jack | 60% | 2025-07-12 | 2025-07-20 | 9
3.3 | ID drawings | Maslinda | 50% | 2025-07-16 | 2025-07-30 | 15
4 | Submission to Authorities (PBT, BOMBA, TNB, IWK) | Azlan, Maslinda, Jack | 40% | 2025-07-21 | 2025-08-04 | 15
4.1 | DBKL Authorities Submission | Azlan | 30% | 2025-07-26 | 2025-08-04 | 10
4.2 | TNB Authorities Submission | Azlan | 20% | 2025-07-31 | 2025-08-08 | 9
4.3 | IWK Authorities Submission | Jack | 10% | 2025-08-05 | 2025-08-19 | 15
5 | Cost estimation & contract signing | John Chew | 8% | 2025-08-10 | 2025-08-24 | 15
8 |  |  | 0% |  | 0 | 1
PHASE 2: Construction / Structural (With Floor-Based Structure)
1 | Site Preparation | SWB - John | 100% | 2025-07-19 | 2025-08-02 | 15 | 15
1.1 | Site clearing & hoarding | SWB - Andrew | 90% | 2025-07-29 | 2025-08-19 | 22 | 22
1.2 | Soil investigation | SWB - Azman | 80% | 2025-08-08 | 2025-09-09 | 33 | 33
PHASE 3: Architectural / Interior Finishing
1 | Flooring Works | SWB - John | 100% | 2025-07-29 | 2025-08-09 | 12 | 12
1.1 | Screeding | SWB - John | 90% | 2025-08-05 | 2025-08-24 | 20
1.2 | Tiling | SWB - John | 80% | 2025-08-12 | 2025-09-15 | 35
PHASE 4: External Works
1 | Drainage & Sewerage | SWB - John | 25% | 2025-07-19 | 2025-08-11 | 23 | 24
1.1 | Underground drainage pipes | SWB - John | 50% | 2025-07-30 | 2025-08-21 | 22 | 23
1.2 | Manholes (drainage) | SWB - John | 50% | 2025-08-10 | 2025-08-31 | 21 | 22
PHASE 5: Testing, Approvals & Handover
1 | Testing & Commissioning | SWB - John | 90% | 2025-07-29 | 2025-08-03 | 5 | 6
1.1 | Electrical, water pressure, air-cond, etc. | SWB - John | 80% | 2025-08-03 | 2025-08-08 | 5 | 6
2 | Snagging & Rectification | Azlan, Maslinda, Jack, John | 70% | 2025-08-08 | 2025-08-28 | 20 | 21
note: Insert new rows ABOVE this one (https://www.ShockwaveBuilders.com/free-construction-gantt-chart-template) | bar: 2025-06-30 to 2025-09-17
1. Change the Company LOGO & Company DETAIL.
2. Fill in the CELL with BORDERS (Project Title, Manager, Start Date, Display Week)
3. The PROJECT START will determine the week the project start and will always show the full week starting on Monday.
4. The TODAY DATE will be display in the chart with 2 RED LINES.
5. The DISPLAY WEEK if you change the week to "14" it will display the chart starting for Week 14. (week 1 to week 13 will be hidden/for easy printing)
6. We have use the INCREASE INDENT to differentiate the sub-task
7. Once you fill in the START & WORK DAYS the END date will automatically change.
8. When you change the % of PROGRESS the progress bar on the right will display the work completion.
9. To add ADDITIONAL ROW you just need to insert row and the formular will retain. (if the formular do not appear you can copy & paste the previous row)
10. The Gantt Chart / Project Schedule are pre-prepare for a 1 years project you can delete the extra column or change the DISPLAY WEEK as the project progresses.
Instruction:
1. Change the Company LOGO & Company DETAIL.
2. Fill in the CELL with BORDERS (Project Title, Manager, Start Date, Display Week)
3. The PROJECT START will determine the week the project start and will always show the full week starting on Monday.
4. The TODAY DATE will be display in the chart with 2 RED LINES.
5. The DISPLAY WEEK if you change the week to "14" it will display the chart starting for Week 14. (week 1 to week 13 will be hidden/for easy printing)
6. We have use the INCREASE INDENT to differentiate the sub-task
7. Once you fill in the START & WORK DAYS the END date will automatically change.
8. When you change the % of PROGRESS the progress bar on the right will display the work completion.
9. To add ADDITIONAL ROW you just need to insert row and the formular will retain. (if the formular do not appear you can copy & paste the previous row)
10. The Gantt Chart / Project Schedule are pre-prepare for a 1 years project you can delete the extra column or change the DISPLAY WEEK as the project progresses.