## PMO Setup Checklist
PMO Setup Checklist
Organisation: [name] PMO sponsor: [name] Target go-live: [date]
Step | Status | Owner | Target date | Notes
1. Mandate & sponsorship
Write the PMO's purpose and what success looks like (1–2 sentences)
Secure a named executive sponsor at the leadership table
Agree the problems the PMO will solve first
2. Operating model
Choose PMO type: supportive / controlling / directive
Choose reach: departmental or enterprise (EPMO)
Confirm the model your organisation can realistically absorb
3. Services & scope
Decide initial services (start with reporting + governance)
Define what is in scope and out of scope for v1
Map services to the pain they solve
4. Governance & standards
Define the project lifecycle stages and gates
Create core templates: business case, plan, status report, RAID log
Agree how projects enter and exit the portfolio
5. Tooling
Confirm starting tool (spreadsheet is fine for a few projects)
Define when you'll graduate to a PPM tool (portfolio rollup needed)
Confirm data residency / Microsoft-tenant requirements
6. Metrics & reporting
Agree the handful of measures leadership cares about
Design one clear portfolio dashboard / report
7. Roll-out & adoption
Communicate the 'why' to delivery teams
Train people on the standards; run a pilot group
Plan a visible early win in the first 30–60 days
8. Review & mature
Set a quarterly review of what's working
Add services as the organisation is ready

## How to use
PMO Setup Checklist — how to use
Work top to bottom. Each phase builds on the last — don't skip the mandate and sponsor.
Use the Status dropdown (Not started / In progress / Done) to track progress.
Assign one owner and a target date to each step.
Aim for a visible early win in the first 30–60 days — usually 'leadership can finally see the portfolio'.
When spreadsheets stop scaling, NextGen PPM gives your PMO portfolio-wide governance inside your own
Microsoft tenant, with board-ready dashboards from day one. www.nextgenppm.com