## Portfolio Tracker
Project Portfolio Tracker
Organisation: [name] Portfolio owner: [name] Last updated: [date] One row per project — update weekly.
Project name | Owner / PM | Sponsor | Stage | RAG | % complete | Start date | Target end | Next milestone | Budget | Spend to date | Benefit / outcome | Notes / key risk
Finance system upgrade | [Name] | [Sponsor] | Delivery | Amber | 55 | 2026-02-01 | 2026-09-30 | UAT sign-off (Aug) | 120000 | 68000 | Faster monthly close | Test environment delay
Customer portal | [Name] | [Sponsor] | Initiation | Green | 10 | 2026-06-01 | 2027-01-31 | Business case approval | On track
Data migration (Project Online) | [Name] | [Sponsor] | Delivery | Red | 40 | 2026-03-01 | 2026-09-30 | Cutover plan agreed | Supplier may miss deadline

## Portfolio Summary
Portfolio Summary
Total projects | 3
Green | 1
Amber | 1
Red | 1
Total budget | 120000
Total spend to date | 68000
Counts update automatically as you fill the tracker (delete the grey example rows first).

## How to use
Project Portfolio Tracker — how to use
One row per project. Update weekly and before every portfolio/board review.
Use the Stage and RAG dropdowns. RAG cells colour automatically: Green = on track, Amber = watch, Red = act now.
Get each project owner to update their own row so the data stays current and owned.
In review, walk the Reds and Ambers first, agree actions, and use the tracker to make decisions — reprioritise, move resources, or stop projects.
The Portfolio Summary tab counts your RAGs and totals budget/spend automatically.
When the spreadsheet stops scaling, NextGen PPM gives you a live portfolio dashboard inside your own
Microsoft tenant — updated by your teams in real time. www.nextgenppm.com